## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BAISPUR AND ADJOINING MOUJAS PWSS | SM/12290 | New | Material Requisition To Resource Division |  |  | RTOR000126/2022-2023 | 2410/TD | 16/01/2023 | 16/01/2023 | Resource Division | 21.35 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | BAISPUR AND ADJOINING MOUJAS PWSS | SM/12290 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAISPUR and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001346/2022-2023 | 2357/W/MMD | 31/12/2022 | 29/06/2023 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BAISPUR AND ADJOINING MOUJAS PWSS | SM/12290 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Baispur PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000185/2024-2025 | 2195/TD | 09/07/2024 | 19/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BAISPUR AND ADJOINING MOUJAS PWSS | SM/12290 | New | Material Requisition To Resource Division |  |  | RTOR000009/2025-2026 | 2071/TD | 12/08/2025 | 12/08/2025 | Resource Division | 7.71 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | BAISPUR AND ADJOINING MOUJAS PWSS | SM/12290 | New | Quotation Bill for New Service connection at T/W NO-I Of BAISPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004970204/QUOT/03/1383 DT. 19-11-2024 Application NO- 2004970204 Application type-New connection Consumer Id- 204449426 |  |  | BILL/03244/2024-2025 | C122405685539 | 05/12/2024 | 05/12/2024 | WBSEDCL | 10.24 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | BAISPUR AND ADJOINING MOUJAS PWSS | SM/12290 | New | Quotation Bill for New Service connection at T/W NO-II Of BAISPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004962430/QUOT/03 DT. 12-10-2024 Application NO- 2004962430 Application type-New connection Consumer Id- 204443612 |  |  | BILL/03275/2024-2025 | C122405543180 | 05/12/2024 | 05/12/2024 | WBSEDCL | 5.21 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BAISPUR AND ADJOINING MOUJAS PWSS | SM/12290 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 189.99 | 0.97 | 51
Total | [13 empty] | 19575.94 | 190.94 | 0.98