## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Tamluk Division | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS | SM/12291 | New | Material Requisition To Resource Division |  |  | RTOR000252/2022-2023 | 2714/TD | 06/02/2023 | 06/02/2023 | Resource Division | 61 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Tamluk Division | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS | SM/12291 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1648 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Uttar Daidpur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000482/2023-2024 | 1568/TD | 19/07/2023 | 15/01/2024 | M/S JOY MAA DURGA ENTERPRISE | 488.61 | 243.96 | 49.93 | 60
3 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS | SM/12291 | New | Quotation Bill for New Service connection at T/W NO-II Of UTTAR DAUDPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004852092/QUOT/03/562 DT. 07-08-2024 Application NO- 2004852092 Application type-New connection Consumer Id- 204373375 |  |  | BILL/02123/2024-2025 | C092403062421 | 04/09/2024 | 04/09/2024 | WBSEDCL | 6.07 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS | SM/12291 | New | Uttar Daudpur W/S scheme PH-I Application no.-2004523051 ref.-204157004 |  |  | BILL/03189/2023-2024 | BP-2023-24-485 | 27/12/2023 | 27/12/2023 | WBSEDCL | 3.69 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS | SM/12291 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR DAIDPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001358/2022-2023 | 2369/W/MMD | 31/12/2022 | 29/06/2023 | BHABANI PRASAD MANNA | 23.7 | 11.06 | 46.68 | 85
Total | [13 empty] | 583.07 | 255.02 | 43.74