## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Material Requisition To Resource Division |  |  | RTOR000189/2022-2023 | 2388/TD | 16/01/2023 | 16/01/2023 | Resource Division | 34.82 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Material Requisition To Resource Division |  |  | RTOR000183/2023-2024 | 632/W | 20/02/2024 | 20/02/2024 | Resource Division | 8.94 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Pachahari W/S scheme PH-I Application.-2004537390 Ref.-204168886 |  |  | BILL/03297/2023-2024 | BP-2023-24-531 | 11/01/2024 | 11/01/2024 | WBSEDCL | 4.08 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Pachahari W/S scheme PH-II Application.-2004537398 Ref.-204168891 |  |  | BILL/03298/2023-2024 | BP-2023-24-532 | 11/01/2024 | 11/01/2024 | WBSEDCL | 3.16 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Laying distribution pipe line & Accommodate FHTC (170 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | Assistant Engineer | Junior Engineer | ORD/000875/2022-2023 | 3211/TD | 14/03/2023 | 31/01/2026 | KAMAL KUMAR BERA | 19.49 | 5.93 | 30.43 | 45
6 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Pump House, Laying distribution pipe line & Accommodate FHTC (420 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000873/2022-2023 | 3210/TD | 14/03/2023 | 23/01/2026 | ABHIJIT BERA | 82.33 | 57.41 | 69.73 | 50
7 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Laying distribution pipe line & Accommodate FHTC (75nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - E) | Assistant Engineer | Junior Engineer | ORD/000876/2022-2023 | 3212/TD | 14/03/2023 | 03/04/2023 | PARTHA CONSTRUCTION | 9.77 | 4.15 | 42.52 | 45
8 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Laying distribution pipe line, Boundary Wall & Accommodate FHTC ( 430 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | Assistant Engineer | Junior Engineer | ORD/000912/2022-2023 | 3561/TD | 29/03/2023 | 22/05/2025 | OM ENTERPRISE | 80.86 | 42.25 | 52.24 | 55
9 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 55.54 | 0.26 | 11
10 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (357 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000634/2023-2024 | 2443/TD | 19/09/2023 | 01/08/2025 | THREE MAA ENTERPRISE | 226.83 | 107.43 | 47.36 | 32
11 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Laying of Left out Distribution pipe line by HDPE pipes with allied works for PACHHARI PWSS (PART-B) within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-B) | Assistant Engineer | Junior Engineer | ORD/000533/2024-2025 | 211/TD | 15/01/2025 | 26/01/2026 | SAURAV HAZRA | 12.27 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Drum Sheet Walling & allied works of Pachhari PWSS (PART-A) in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer |  | ORD/000319/2024-2025 | 3222/TD | 01/10/2024 | 26/10/2024 | THREE MAA ENTERPRISE | 9.45 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | PACHAHRI & ADJOINING MOUJAS PWSS | SM/12292 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
Total | [13 empty] | 21833.98 | 272.7 | 1.25