## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | SM/12293 | New | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1373 nos) under JJM with allied work of DAKSHIN PATHAR BERYA AND IT'S ADJOINING MOUJAS PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000278/2023-2024 | 555/TD | 12/05/2023 | 26/04/2026 | PATHIK PABAN NANDI | 460.76 | 167.47 | 36.35 | 50
2 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | SM/12293 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | SM/12293 | New | Material Requisition To Resource Division |  |  | RTOR000340/2022-2023 | 2967/TD | 27/02/2023 | 27/02/2023 | Resource Division | 35.37 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | SM/12293 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
5 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | SM/12293 | New | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 633/W | 20/02/2024 | 20/02/2024 | Resource Division | 8.46 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | SM/12293 | New | Bill for damage of Road flank / hard shoulder due to cutting of hard shoulder and road flank on Itaberia Mugberia Road from 1.25 Km. To 3.10 Km. for laying water pipe line of Dakshin Patherbaria PWSS. |  |  | BILL/00991/2024-2025 | BP-2024-25-494 | 01/10/2024 | 01/10/2024 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.12 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | SM/12293 | New | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 30/10/2024 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | SM/12293 | New | Sinking of (2 nos.) 250 x 150mm Dia and 230mtr deep tubewell Drilling by Direct Rotary method with 150mm dia. uPVC Strainer of 30mtr length all complete including cost of materials for 1st & 2nd Tubewell of Dakshin Patharberya PWSS under Bhagwanpur-II Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, Purba Medinipur PHE Dte |  |  | ORD/000579/2024-2025 | 457/TD | 04/02/2025 | 16/03/2025 | B. K. ENTERPRISE | 26.35 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | SM/12293 | New | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division |  |  | BILL/00708/2025-2026 |  | 20/08/2025 | 20/08/2025 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.17 | 0 | 0 | 0
Total | [13 empty] | 21937.04 | 167.47 | 0.76