## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | ILASHPUR AND ADJOINING MOUJAS PWSS | SM/12294 | New | Material Requisition To Resource Division |  |  | RTOR000196/2022-2023 | 2385/TD | 16/01/2023 | 16/01/2023 | Resource Division | 20.13 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | ILASHPUR AND ADJOINING MOUJAS PWSS | SM/12294 | New | Electric Quotation for ILASHPUR Water Supply Scheme T/W-I, (Ref. ID-204086226) |  |  | BILL/02895/2023-2024 | BP-2023-24-314 | 01/11/2023 | 01/11/2023 | WBSEDCL | 3.01 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | ILASHPUR AND ADJOINING MOUJAS PWSS | SM/12294 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ILASHPUR and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001357/2022-2023 | 2368/W/MMD | 31/12/2022 | 29/06/2023 | BHABANI PRASAD MANNA | 23.7 | 19.18 | 80.94 | 50
4 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | ILASHPUR AND ADJOINING MOUJAS PWSS | SM/12294 | New | Laying Distribution System (NP-2-27,27-38,38-45,45-47,47-53,53-57,57-61,61-63,63-65,65-67 & 67-71) of pipe line and its allied works for Ilashpur Water Supply Scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000140/2024-2025 | 1923/TD | 07/06/2024 | 02/07/2024 | MMS CONSTRUCTIONS PVT. LTD. | 12.61 | 12.14 | 96.26 | 90
5 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | ILASHPUR AND ADJOINING MOUJAS PWSS | SM/12294 | New | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 88/TD | 05/01/2024 | 05/01/2024 | Resource Division | 12.55 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | ILASHPUR AND ADJOINING MOUJAS PWSS | SM/12294 | New | Payment to WBSEDCL for Shifting of LTOH Line at Siulipur for Ilashpur PWSS under Tamluk Division, PHE Dte. |  |  | BILL/00810/2024-2025 | BP-2024-25-382 | 29/08/2024 | 29/08/2024 | WBSEDCL | 0.81 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | ILASHPUR AND ADJOINING MOUJAS PWSS | SM/12294 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2038 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of ILASHPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000217/2023-2024 | 448/TD | 04/05/2023 | 01/12/2025 | TAPAS SANTRA | 657.13 | 356.42 | 54.24 | 58
8 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | ILASHPUR AND ADJOINING MOUJAS PWSS | SM/12294 | New | Quotation Bill for New Service connection at T/W NO-II Of ILASHPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2005011980/QUOT/03 DT. 18-12-2024 Application NO- 2005011980 Application type-New connection CONSUMER ID: 204475791 |  |  | BILL/03864/2024-2025 | C012539026306 | 21/01/2025 | 21/01/2025 | WBSEDCL | 3.58 | 0 | 0 | 0
Total | [13 empty] | 733.53 | 387.74 | 52.86