## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | NAICHHANPUR AND ADJOINING MOUJAS PWSS | SM/12295 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NAICHHANPUR AND ADJOINING MOUJAS PWSS, Block Moyna, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000168/2023-2024 | 1411/W/MMD | 02/06/2023 | 29/11/2023 | P.K.ENGINEERING | 27.53 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS | SM/12295 | New | Material Requisition To Resource Division |  |  | RTOR000327/2022-2023 | 2989/TD | 27/02/2023 | 27/02/2023 | Resource Division | 16.3 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS | SM/12295 | New | Laying distribution System & Accommodate FHTC (500 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(PART-B) | Assistant Engineer | Junior Engineer | ORD/000891/2022-2023 | 3245/TD | 15/03/2023 | 16/07/2025 | ADHIKARY CONSTRUCTION | 64.64 | 32.51 | 50.29 | 60
4 | PURBA MEDINIPUR | Moyna | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS | SM/12295 | New | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 1568/TD | 23/04/2024 | 23/04/2024 | Resource Division | 9.32 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | NAICHHANPUR AND ADJOINING MOUJAS PWSS | SM/12295 | New | Naichanpur W/S scheme Ph-I Application No.-204543058 Ref.-204175259 |  |  | BILL/03267/2023-2024 | BP-2023-24-514 | 09/01/2024 | 09/01/2024 | WBSEDCL | 2.78 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | NAICHHANPUR AND ADJOINING MOUJAS PWSS | SM/12295 | New | Naichanpur W/S scheme PH-II Application No.-2004543088 Ref.-204175260 |  |  | BILL/03268/2023-2024 | BP-2023-24-513 | 09/01/2024 | 09/01/2024 | WBSEDCL | 4.51 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Moyna | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS | SM/12295 | New | Laying distribution System, Construction of Boundary wall at 1st. & 2nd. Tube well site, Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room, interconnection with laying of 150 mm dia & 200 mm dia DI(K-9) Rising main and Accommodate FHTC (638 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 416/TD | 02/05/2023 | 20/02/2025 | KRISHNENDU SEKHAR DAS | 140.04 | 117.64 | 84 | 74
8 | PURBA MEDINIPUR | Moyna | Central Drilling | NAICHHANPUR AND ADJOINING MOUJAS PWSS | SM/12295 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 47.62 | 0.22 | 11
9 | PURBA MEDINIPUR | Moyna | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS | SM/12295 | New | Laying distribution System, Construction of Pump House & Accommodate FHTC (375 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000890/2022-2023 | 3244/TD | 15/03/2023 | 03/01/2025 | GHOSH ENTERPRISE | 90.18 | 84.46 | 93.65 | 65
10 | PURBA MEDINIPUR | Moyna | Tamluk Division | NAICHHANPUR AND ADJOINING MOUJAS PWSS | SM/12295 | New | Soil investigation & R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(PART-E) | Assistant Engineer | Junior Engineer | ORD/000208/2023-2024 | 417/TD | 02/05/2023 | 20/04/2025 | ARABINDA GHOSH | 113.16 | 90.05 | 79.57 | 46
Total | [13 empty] | 21808.23 | 372.28 | 1.71