## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Material Requisition To Resource Division |  |  | RTOR000127/2022-2023 | 2411/TD | 16/01/2023 | 16/01/2023 | Resource Division | 12.32 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Quotation Bill for New Service connection at T/W NO-II Of SAHARA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004769176/QUOT/03/442 DT. 11-06-2024 Application NO- 2004769176 Application type-New connection Consumer Id- 204327965 |  |  | BILL/01279/2024-2025 | BP-2024-25-333 | 25/06/2024 | 25/06/2024 | WBSEDCL | 3.49 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Quotation Bill for New Service connection at T/W NO-I Of SAHARA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004769073/QUOT/03/443 DT. 11-06-2024 Application NO- 2004769073 Application type-New connection Consumer Id- 204327178 |  |  | BILL/01277/2024-2025 | BP-2024-25-334 | 25/06/2024 | 25/06/2024 | WBSEDCL | 4.79 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAHARA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002032/2022-2023 | 940/W/MMD | 28/03/2023 | 31/07/2025 | SUJOY RANJAN BHOWMICK | 27.69 | 0 | 0 | 60
Total | [13 empty] | 48.3 | 0 | 0