## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Material Requisition To Resource Division |  |  | RTOR000127/2022-2023 | 2411/TD | 16/01/2023 | 16/01/2023 | Resource Division | 12.32 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Quotation Bill for New Service connection at T/W NO-II Of SAHARA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004769176/QUOT/03/442 DT. 11-06-2024 Application NO- 2004769176 Application type-New connection Consumer Id- 204327965 |  |  | BILL/01279/2024-2025 | BP-2024-25-333 | 25/06/2024 | 25/06/2024 | WBSEDCL | 3.49 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Quotation Bill for New Service connection at T/W NO-I Of SAHARA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004769073/QUOT/03/443 DT. 11-06-2024 Application NO- 2004769073 Application type-New connection Consumer Id- 204327178 |  |  | BILL/01277/2024-2025 | BP-2024-25-334 | 25/06/2024 | 25/06/2024 | WBSEDCL | 4.79 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAHARA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002032/2022-2023 | 940/W/MMD | 28/03/2023 | 31/07/2025 | SUJOY RANJAN BHOWMICK | 27.69 | 16.57 | 59.85 | 60
5 | PURBA MEDINIPUR | Egra-I | Tamluk Division | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Sahara PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000228/2024-2025 | 2423/TD | 29/07/2024 | 08/08/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
6 | PURBA MEDINIPUR | Egra-I | Tamluk Division | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Material Requisition To Resource Division |  |  | RTOR000018/2025-2026 | 2096/TD | 12/08/2025 | 12/08/2025 | Resource Division | 7.11 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Egra-I | Tamluk Division | SAHARA AND ADJOINING MOUJAS PWSS | SM/12296 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 172.72 | 0.89 | 51
Total | [13 empty] | 19564.08 | 190.24 | 0.97