## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Material Requisition To Resource Division |  |  | RTOR000120/2022-2023 | 2389/TD | 16/01/2023 | 16/01/2023 | Resource Division | 33.31 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Laying distribution pipe line & Accommodate FHTC (60 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - F) | Assistant Engineer | Junior Engineer | ORD/000844/2022-2023 | 3187/TD | 10/03/2023 | 25/03/2023 | SUSANTA KUMAR KAR | 9.8 | 0 | 0 | 45
3 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Laying distribution pipe line & Accommodate FHTC (300nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | Assistant Engineer | Junior Engineer | ORD/000843/2022-2023 | 3186/TD | 10/03/2023 | 04/04/2023 | BADAL CHANDRA GOLE | 37.34 | 0 | 0 | 48
4 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Pump House, Laying distribution pipe line, & Accommodate FHTC (270 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000840/2022-2023 | 3184/TD | 10/03/2023 | 04/04/2023 | SUBHENDU HAZRA | 48.38 | 0 | 0 | 50
5 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Basudeb Berya PWSS at Bhagwanpur-II Block under Tamluk Division,PHE Dte. | Assistant Engineer |  | ORD/001052/2023-2024 | 382/TD | 29/01/2024 | 08/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
6 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 634/W | 20/02/2024 | 20/02/2024 | Resource Division | 6.55 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Additional Quotation Bill cost due to Modification for NSC of PHE AT Site- BASUDEVBERIA W/S SCHEME, T/W NO-I Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-MDK/QOUT/253 DT. 16-05-2024 Application NO- 100000108115 DT. 16-05-2024 Application type-ADDITIONAL QUOTATION REF. Id- 860300165 |  |  | BILL/01128/2024-2025 | BP-2024-25-241 | 06/06/2024 | 06/06/2024 | WBSEDCL | 0.59 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Quotation Bill for New Service connection at T/W NO-II Of BASUDEVBERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558723/QUOT/03 DT. 10-01-2024 Application NO- 2004558723 Application type-New connection Consumer Id- 204187848 |  |  | BILL/04388/2023-2024 | BP-2023-24-829 | 13/03/2024 | 13/03/2024 | WBSEDCL | 3.14 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Quotation Bill for New Service connection at T/W NO-I Of BASUDEVBERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558731/QUOT/03 DT. 27-02-2024 Application NO- 2004558731 Application type-New connection Consumer Id- 204187847 |  |  | BILL/04390/2023-2024 | BP-2023-24-828 | 13/03/2024 | 13/03/2024 | WBSEDCL | 3.48 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Laying distribution pipe line, Boundary Wall & Accommodate FHTC ( 250 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | Assistant Engineer | Junior Engineer | ORD/000841/2022-2023 | 3185/TD | 10/03/2023 | 24/03/2026 | M/S. NEW DINDA ENTERPRISE | 48.13 | 0 | 0 | 50
11 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
12 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 10/09/2024 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
13 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
14 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | SM/12297 | New | Laying of Distribution pipe line by HDPE pipes with allied works of BASUDEVBERIA PWSS within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PART-G) | Assistant Engineer | Junior Engineer | ORD/001148/2023-2024 | 568/TD | 15/02/2024 | 05/11/2024 | PARTHA CONSTRUCTION | 6.83 | 0 | 0 | 90
Total | [13 empty] | 21550.88 | 0 | 0