## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Tamluk Division | ERENDA AND ADJOINING MOUJAS PWSS | SM/12298 | New | Material Requisition To Resource Division |  |  | RTOR000254/2022-2023 | 2713/TD | 06/02/2023 | 06/02/2023 | Resource Division | 29.89 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | ERENDA AND ADJOINING MOUJAS PWSS | SM/12298 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ERENDA and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001356/2022-2023 | 2367/W/MMD | 31/12/2022 | 29/06/2023 | BHABANI PRASAD MANNA | 23.7 | 10.96 | 46.25 | 45
3 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | ERENDA AND ADJOINING MOUJAS PWSS | SM/12298 | New | Quotation Bill for New Service connection at T/W NO-II Of ERENDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004792956/QUOT/03/379 DT. 02-07-2024 Application NO- 2004792956 Application type-New connection Consumer Id- 204345868 |  |  | BILL/01701/2024-2025 | BP-2024-25-494 | 29/07/2024 | 29/07/2024 | WBSEDCL | 3.96 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | ERENDA AND ADJOINING MOUJAS PWSS | SM/12298 | New | Erenda W/S scheme PH-I Application no.-2004523042 ref.-204156895 |  |  | BILL/03192/2023-2024 | BP-2023-24-482 | 27/12/2023 | 27/12/2023 | WBSEDCL | 4.3 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-II | Tamluk Division | ERENDA AND ADJOINING MOUJAS PWSS | SM/12298 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1648 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Erenda PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000491/2023-2024 | 1592/TD | 21/07/2023 | 23/11/2025 | MUKHERJEE CONSTRUCTION | 504.12 | 221.63 | 43.96 | 62
Total | [13 empty] | 565.97 | 232.6 | 41.1