## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GATHRA AND ADJOINING MOUJAS PWSS | SM/12299 | New | Material Requisition To Resource Division |  |  | RTOR000210/2022-2023 | 2468/TD | 16/01/2023 | 16/01/2023 | Resource Division | 17.41 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | GATHRA AND ADJOINING MOUJAS PWSS | SM/12299 | New | Electric Quotation for GOTHRA Water Supply Scheme , (Ref. ID-204075850) |  |  | BILL/02187/2023-2024 | BP-2023-24-238 | 12/09/2023 | 12/09/2023 | WBSEDCL | 3.98 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | GATHRA AND ADJOINING MOUJAS PWSS | SM/12299 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GATHRA and ADJOINING MOUJAS, Block Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001355/2022-2023 | 2366/W/MMD | 31/12/2022 | 29/06/2023 | ABHIJIT BASU | 23.69 | 11.08 | 46.75 | 35
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GATHRA AND ADJOINING MOUJAS PWSS | SM/12299 | New | Work order for installation of 18 nos Dispaly Board at different PWSS works site under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000197/2024-2025 | 2279/TD | 18/07/2024 | 25/07/2024 | GLOBAL TRADE | 3.95 | 3.78 | 95.61 | 100
5 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GATHRA AND ADJOINING MOUJAS PWSS | SM/12299 | New | Land development work at Headwork Site of Gathra Water Supply Scheme within Sahid Matangini Development Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000127/2024-2025 | 1925/TD | 07/06/2024 | 21/06/2024 | S. P. ENTERPRISE (GSTIN- 19FLFPR7861R1ZS) | 4.23 | 4.18 | 98.77 | 100
6 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GATHRA AND ADJOINING MOUJAS PWSS | SM/12299 | New | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 129/TD | 05/01/2024 | 05/01/2024 | Resource Division | 11.19 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | GATHRA AND ADJOINING MOUJAS PWSS | SM/12299 | New | Quotation Bill for Gathra W/S Scheme T/W-II Application No=2005003708 Reference ID=204470377 |  |  | BILL/03670/2024-2025 |  | 18/12/2024 | 18/12/2024 | WBSEDCL | 3.06 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | GATHRA AND ADJOINING MOUJAS PWSS | SM/12299 | New | Gathra W/S scheme H/W site. Application No.-100000094421 Ref.-860286461 |  |  | BILL/03303/2023-2024 | BP-2023-24-544 | 15/01/2024 | 15/01/2024 | WBSEDCL | 0.34 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GATHRA AND ADJOINING MOUJAS PWSS | SM/12299 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1816 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GATHRA PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2023-2024 | 218/TD | 17/04/2023 | 01/04/2026 | TAPAS SANTRA | 495.61 | 270.77 | 54.63 | 75
Total | [13 empty] | 563.46 | 289.79 | 51.43