## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the district of Purba Medinipur. | SM/12301 | Retrofitting | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the District of Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000390/2022-2023 | 1423/TD | 26/09/2022 | 26/10/2022 | SANKHA ENTERPRISE | 86.77 | 68.76 | 79.24 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the district of Purba Medinipur. | SM/12301 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000216/2023-2024 | 1115/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
Total | [13 empty] | 86.96 | 68.76 | 79.07