## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. | SM/12302 | Retrofitting | Providing FHTC with allied works of Nijkasba & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000544/2022-2023 | 2163/TD | 19/12/2022 | 13/01/2023 | HARIPADA PATTANAYAK | 35.25 | 33.89 | 96.16 | 70
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. | SM/12302 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 609/TD | 17/05/2023 | 17/05/2023 | Resource Division | 4.7 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. | SM/12302 | Retrofitting | Construction of Boundary Wall (as per Departmental Design & Drawing) for OHR site at Nijkasba W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for East side, North & South Side) | Assistant Engineer | Junior Engineer | ORD/000316/2023-2024 | 487/TD | 10/05/2023 | 24/06/2023 | BIPLAB BAHNI GUCHHAIT | 4.5 | 3.79 | 84.23 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. | SM/12302 | Retrofitting | Laying of left out pipe line by HDPE pipes with allied works of distribution system of Nijkasba W/S Scheme under Contai Sub-Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000765/2025-2026 | 2275/CSD | 09/10/2025 | 08/11/2025 | SAVORIO REALITY LLP | 0.96 | 0 | 0 | 0
Total | [13 empty] | 45.41 | 37.68 | 82.98