## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. | SM/12303 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Baranalgeria Zone-I PWSS under Egra-II Block within Digha Sub-Division of Tamluk Division. | Assistant Engineer | Junior Engineer | ORD/000775/2022-2023 | 2859/TD | 17/02/2023 | 03/04/2023 | DAS CONSTRUCTION | 80.73 | 54.34 | 67.31 | 70
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. | SM/12303 | Retrofitting | Requirement of additional pipeline for Retrofitting to accommodate FHTC under JJM in Baranalgeria Zone-I PWSS under Egra-II Block within Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000664/2023-2024 | 2672/TD | 16/10/2023 | 09/06/2025 | M/S. CHANDI CHARAN MISHRA & CO. | 51.03 | 0 | 0 | 1
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. | SM/12303 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000290/2022-2023 | 2646/TD | 02/02/2023 | 02/02/2023 | Resource Division | 14.41 | 0 | 0 | 0
Total | [13 empty] | 146.17 | 54.34 | 37.18