## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BARDA AND ADJOINING MOUJAS PWSS | SM/12306 | New | Material Requisition To Resource Division |  |  | RTOR000135/2022-2023 | 2419/TD | 16/01/2023 | 16/01/2023 | Resource Division | 27.14 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | BARDA AND ADJOINING MOUJAS PWSS | SM/12306 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARDA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001402/2022-2023 | 2413/W/MMD | 31/12/2022 | 29/06/2023 | ECO ENTERPRISE | 22.8 | 0 | 0 | 35
3 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BARDA AND ADJOINING MOUJAS PWSS | SM/12306 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Barda PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000170/2024-2025 | 2082/TD | 24/06/2024 | 04/07/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BARDA AND ADJOINING MOUJAS PWSS | SM/12306 | New | Quotation for new service connection at T/W-I of Barada under MMD,PHE DTE, Block-Egra-I, Chorpalia CCC Application no-2004811995 CON ID-204352240 |  |  | BILL/00635/2024-2025 | BP-2024-25-312 | 02/08/2024 | 02/08/2024 | WBSEDCL | 20.24 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | BARDA AND ADJOINING MOUJAS PWSS | SM/12306 | New | Quotation Bill for New Service connection at T/W NO-II Of BARADA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004847092/QUOT/03/1184 DT. 13-08-2024 Application NO- 2004847092 Application type-New connection Consumer Id- 204372857 |  |  | BILL/02122/2024-2025 | C082448216760 | 02/09/2024 | 02/09/2024 | WBSEDCL | 3.55 | 0 | 0 | 0
Total | [13 empty] | 74.68 | 0 | 0