## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. | SM/12307 | New | Material Requisition To Resource Division |  |  | RTOR000200/2022-2023 | 2462/TD | 16/01/2023 | 16/01/2023 | Resource Division | 17.76 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. | SM/12307 | New | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 1651/TD | 29/04/2024 | 29/04/2024 | Resource Division | 7.38 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. | SM/12307 | New | Quotation Bill for New Service connection at T/W NO-I Of KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004781161/QUOT/03 DT. 19-06-2024 Application NO- 2004781161 Application type-New connection Consumer Id- 204333913 |  |  | BILL/01330/2024-2025 | BP-2024-25-358 | 01/07/2024 | 01/07/2024 | WBSEDCL | 3.42 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. | SM/12307 | New | Quotation Bill for New Service connection at T/W NO-II Of KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886291/QUOT/03/582 DT. 06-09-2024 Application NO- 2004886291 Application type-New connection Consumer Id- 204391659 |  |  | BILL/02450/2024-2025 | C092443181197 | 27/09/2024 | 27/09/2024 | WBSEDCL | 3.46 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. | SM/12307 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALYANPUR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001348/2022-2023 | 2359/W/MMD | 31/12/2022 | 30/06/2025 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 0 | 80
6 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. | SM/12307 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000678/2023-2024 | 2703/TD | 20/10/2023 | 01/07/2025 | S & P ENTERPRISE | 1928.99 | 23.24 | 1.2 | 30
Total | [13 empty] | 1983.8 | 23.24 | 1.17