## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | JERTHAN AND ADJOINING MOUJAS PWSS | SM/12308 | New | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 2420/TD | 16/01/2023 | 16/01/2023 | Resource Division | 34.51 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | JERTHAN AND ADJOINING MOUJAS PWSS | SM/12308 | New | Quotation Bill for New Service connection at T/W NO-I Of JERTHAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004847107/QUOT/03/1183 DT. 13-08-2024 Application NO- 2004847107 Application type-New connection Consumer Id- 204372867 |  |  | BILL/02121/2024-2025 | C082448274884 | 02/09/2024 | 02/09/2024 | WBSEDCL | 10.86 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | JERTHAN AND ADJOINING MOUJAS PWSS | SM/12308 | New | Quotation Bill for New Service connection at T/W NO-II Of JERTHAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004812325/QUOT/03/814 DT. 09-07-2024 Application NO- 2004812325 Application type-New connection Consumer Id- 204352202 |  |  | BILL/01587/2024-2025 | BP-2024-25-450 | 23/07/2024 | 23/07/2024 | WBSEDCL | 6.77 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | JERTHAN AND ADJOINING MOUJAS PWSS | SM/12308 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JERTHAN and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001371/2022-2023 | 2382/W/MMD | 31/12/2022 | 31/05/2026 | ECO ENTERPRISE | 25.26 | 13.35 | 52.87 | 40
5 | PURBA MEDINIPUR | Egra-I | Tamluk Division | JERTHAN AND ADJOINING MOUJAS PWSS | SM/12308 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Jerthan PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000474/2024-2025 | 3763/TD | 10/12/2024 | 09/01/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
Total | [13 empty] | 78.35 | 13.35 | 17.04