## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Central Drilling | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Sar Berya W/S Scheme(TW-IV), Bhagawanpur-I block under Purba medinipur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000017/2023-2024 | 55/CDD | 06/04/2023 | 06/05/2023 | ASHUTOSH DAS & CO | 13.27 | 0 | 0 | 100
2 | PURBA MEDINIPUR | Bhagawanpur-I | Central Drilling | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 300Mtrs. Depth ) by utilising Departmental machineries for Sarberya W/S Scheme (TW-I) Block Bhagwanpur, under Purba Midnapur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000052/2023-2024 | 549/CDD | 02/06/2023 | 02/07/2023 | CHANDA ENTERPRISE | 21.55 | 0 | 0 | 100
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Material Requisition To Resource Division |  |  | RTOR000250/2022-2023 | 2719/TD | 06/02/2023 | 06/02/2023 | Resource Division | 16.76 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Electric Quotation for SARBERYA Water Supply Scheme T/W-I, (Ref. ID-204090827) |  |  | BILL/02894/2023-2024 | BP-2023-24-315 | 01/11/2023 | 01/11/2023 | WBSEDCL | 3.24 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Central Drilling | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | PROVIDING DRIILING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SARBERYA W/S SCHEME (TW-I), UNDER PASCHIM MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000386/2022-2023 | 1726/CDD | 29/12/2022 | 28/01/2023 | MENAKA ENTERPRISE | 11.86 | 0 | 0 | 100
6 | PURBA MEDINIPUR | Bhagawanpur-I | Central Drilling | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Providing Drilling Crew and other allied works for construction of Tube Well (250mm x 150mm x280 Mtrs. Depth) by utilising Departmental machineries for Dakshin Kalamdan and Sarberya (T/W-I & II) under Purba Medinipur District, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000061/2023-2024 | 854/CDD | 10/07/2023 | 09/08/2023 | MENAKA ENTERPRISE | 31.45 | 0 | 0 | 100
7 | PURBA MEDINIPUR | Bhagawanpur-I | Central Drilling | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Sar Berya W/S Scheme (T/W-III) , Bhagawanpur-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000142/2023-2024 | 56/CDD | 06/04/2023 | 30/04/2024 | ASHUTOSH DAS & CO | 13.27 | 0 | 0 | 100
8 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 289/TD | 17/01/2024 | 17/01/2024 | Resource Division | 11.04 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 111/TD | 05/01/2024 | 05/01/2024 | Resource Division | 12.91 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Electric Quotation for SARBERIYA Water Supply Scheme T/W-II, (Ref. ID-204147802) |  |  | BILL/03136/2023-2024 | BP-2023-24-410 | 09/12/2023 | 09/12/2023 | WBSEDCL | 3.12 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Electric Quotation for SARBERIYA Water Supply Scheme T/W-I, (Ref. ID-204147803) |  |  | BILL/03135/2023-2024 | BP-2023-24-411 | 09/12/2023 | 09/12/2023 | WBSEDCL | 3.32 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Quotation Bill for New Service connection at T/W NO-II Of SARBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818488/QUOT/03 DT. 12-07-2024 Application NO- 2004818488 Application type-New connection Consumer Id- 204355506 |  |  | BILL/01888/2024-2025 | BP-2024-25-553 | 08/08/2024 | 08/08/2024 | WBSEDCL | 3.6 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SARBERYA and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001361/2022-2023 | 2372/W/MMD | 31/12/2022 | 31/08/2025 | DIPALI CONSTRUCTION | 23.68 | 0 | 0 | 85
14 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | SM/12310 | New | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2095 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SARBERYA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000227/2023-2024 | 453/TD | 04/05/2023 | 28/08/2025 | TARUN KOLEY | 640.74 | 0 | 0 | 40
Total | [13 empty] | 809.78 | 0 | 0