## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. | SM/12318 | New | Material Requisition To Resource Division |  |  | RTOR000176/2022-2023 | 2434/TD | 16/01/2023 | 16/01/2023 | Resource Division | 39.7 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. | SM/12318 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Chongra PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000880/2023-2024 | 202/TD | 10/01/2024 | 20/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. | SM/12318 | New | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 1561/TD | 23/04/2024 | 23/04/2024 | Resource Division | 11.88 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. | SM/12318 | New | Quotation of New service connection at Chongra w/s scheme PH I at Moyna Block in the District of Purba Medinipur under MMD PHE Dte. (App ID 2004653990 Con ID 204255037) |  |  | BILL/00235/2024-2025 | BP-2024-25-32 | 15/04/2024 | 15/04/2024 | WBSEDCL | 15.26 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. | SM/12318 | New | Quotation of New service connection at Chongra w/s scheme PH II at Moyna Block in the District of Purba Medinipur under MMD PHE Dte. (App ID 2004653966 Con ID 204255035) |  |  | BILL/00240/2024-2025 | BP-2024-25-33 | 15/04/2024 | 15/04/2024 | WBSEDCL | 8.93 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. | SM/12318 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHONGRA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001362/2022-2023 | 2373/W/MMD | 31/12/2022 | 20/12/2024 | DIPALI CONSTRUCTION | 23.68 | 13.53 | 57.15 | 50
7 | PURBA MEDINIPUR | Moyna | Tamluk Division | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. | SM/12318 | New | Instalation of display Board at 5 nos { 1. CHONGRA PWSS( PUMP HOUSE -1) , 2. BASANTA CHAK PWSS( PUMP HOUSE 1 & 2), 3. GOKUL NAGAR PWSS( PUMP HOUSE 1 & 2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000212/2025-2026 | 57/RWS/TSD | 06/05/2025 | 13/05/2025 | SUDIP MANNA | 0.83 | 0 | 0 | 100
8 | PURBA MEDINIPUR | Moyna | Tamluk Division | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. | SM/12318 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 287.31 | 2.79 | 75
Total | [13 empty] | 10411.83 | 301.8 | 2.9