## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. | SM/12319 | New | Material Requisition To Resource Division |  |  | RTOR000145/2022-2023 | 2449/TD | 16/01/2023 | 16/01/2023 | Resource Division | 32.88 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. | SM/12319 | New | Quotation Bill for New Service connection at T/W NO-II Of TAPINDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835302/QUOT/03 DT. 26-07-2024 Application NO- 2004835302 MEMO NO: AMR/PHE/285 DT.26/7/2024 Application type-New connection Consumer Id- 204365759 |  |  | BILL/01862/2024-2025 | BP-2024-25-536 | 07/08/2024 | 07/08/2024 | WBSEDCL | 1.98 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. | SM/12319 | New | Quotation Bill for New Service connection at T/W NO-I Of TAPINDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004834992/QUOT/03 DT. 26-07-2024 Application NO- 2004834992 MEMO NO: AMR/PHE/284 DT.26/7/2024 Application type-New connection Consumer Id- 204365754 |  |  | BILL/01861/2024-2025 | BP-2024-25-537 | 07/08/2024 | 07/08/2024 | WBSEDCL | 6.84 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. | SM/12319 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 123.85 | 0.63 | 51
5 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. | SM/12319 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TAPINDA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001345/2022-2023 | 2356/W/MMD | 31/12/2022 | 31/08/2025 | SOUMEN ELECTRIC | 21.61 | 15.29 | 70.75 | 61
Total | [13 empty] | 19571.02 | 139.14 | 0.71