## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. | SM/12320 | New | Material Requisition To Resource Division |  |  | RTOR000159/2022-2023 | 2422/TD | 16/01/2023 | 16/01/2023 | Resource Division | 39.03 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. | SM/12320 | New | Quotation Bill for New Service connection at T/W NO-II Of ALANGIRI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674883/QUOT/03 DT. 09-04-2024 Application NO- 2004674883 Application type-New connection Consumer Id- 204269736 |  |  | BILL/00509/2024-2025 | BP-2024-25-85 | 24/04/2024 | 24/04/2024 | WBSEDCL | 6.04 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. | SM/12320 | New | Quotation Bill for New Service connection at T/W NO-I Of ALANGIRI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674870/QUOT/03 DT. 09-04-2024 Application NO- 2004674870 Application type-New connection Consumer Id- 204269908 |  |  | BILL/00507/2024-2025 | BP-2024-25-84 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.15 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. | SM/12320 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ALANGIRI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001406/2022-2023 | 2417/W/MMD | 31/12/2022 | 31/05/2025 | RITESH ENTERPRISE | 22.81 | 10.72 | 47.01 | 80
5 | PURBA MEDINIPUR | Egra-I | Tamluk Division | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. | SM/12320 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Alangiri PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000473/2024-2025 | 3762/TD | 10/12/2024 | 09/01/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
6 | PURBA MEDINIPUR | Egra-I | Tamluk Division | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. | SM/12320 | New | Material Requisition To Resource Division |  |  | RTOR000007/2025-2026 | 2081/TD | 12/08/2025 | 12/08/2025 | Resource Division | 9.22 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Egra-I | Tamluk Division | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. | SM/12320 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 196.57 | 1.01 | 51
Total | [13 empty] | 19588.91 | 207.29 | 1.06