## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Tamluk Division | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. | SM/12321 | New | Material Requisition To Resource Division |  |  | RTOR000256/2022-2023 | 2711/TD | 06/02/2023 | 06/02/2023 | Resource Division | 42.6 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. | SM/12321 | New | Quotation Bill for New Service connection at T/W NO-II Of UTTAR SILAMPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004672028/QUOT/03/45 DT. 05-04-2024 Application NO- 2004672028 Application type-New connection Consumer Id- 204266730 |  |  | BILL/00503/2024-2025 | BP-2024-25-94 | 24/04/2024 | 24/04/2024 | WBSEDCL | 5.1 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. | SM/12321 | New | Quotation Bill for New Service connection at T/W NO-I Of UTTAR SILAMPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004672007/QUOT/03/46 DT. 05-04-2024 Application NO- 2004672007 Application type-New connection Consumer Id- 204266731 |  |  | BILL/00511/2024-2025 | BP-2024-25-93 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.64 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. | SM/12321 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR SILAMPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001579/2022-2023 | 462/W/MMD | 20/03/2023 | 02/03/2025 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 20.72 | 90.9 | 80
5 | PURBA MEDINIPUR | Egra-II | Tamluk Division | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. | SM/12321 | New | Sinking of Tube Well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1155 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Uttar Silampur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000488/2023-2024 | 1565/TD | 19/07/2023 | 08/07/2025 | ORIENT CONSTRUCTION | 431.66 | 224.96 | 52.12 | 60
Total | [13 empty] | 505.79 | 245.68 | 48.57