## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. | SM/12322 | New | Material Requisition To Resource Division |  |  | RTOR000264/2022-2023 | 2701/TD | 06/02/2023 | 06/02/2023 | Resource Division | 27.23 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. | SM/12322 | New | Material Requisition To Resource Division |  |  | RTOR000169/2023-2024 | 113/TD | 05/01/2024 | 05/01/2024 | Resource Division | 9.76 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. | SM/12322 | New | QUOTATION FOR NEW SERVICE CONNECTION AT TW-1 OF SANTRA WS SCHEME UNDER MMD PHE DTE , BLOCK-RAMNAGAR-1, DIGHA CCC APPLICATION NO-2004746369 CON ID-204313990 |  |  | BILL/01141/2024-2025 | BP-2024-25-255 | 06/06/2024 | 06/06/2024 | WBSEDCL | 6.93 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. | SM/12322 | New | Quotation Bill for New Service connection at T/W NO-II Of SANTRA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004746350/QUOT/03 DT. 22-05-2024 Application NO- 2004746350 Application type-New connection Consumer Id- 204313989 |  |  | BILL/01136/2024-2025 | BP-2024-25-256 | 06/06/2024 | 06/06/2024 | WBSEDCL | 6.93 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. | SM/12322 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SANTRA and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001580/2022-2023 | 463/W/MMD | 20/03/2023 | 01/03/2025 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 0 | 0 | 90
6 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. | SM/12322 | New | Sinking of Tube Well ,Construction of 250 Cu.m. Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2852 Nos) For 2 nos Pipe Water Supply Scheme including (Santra & Purba Mukundapur) including two years Operation & Maintainance within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000682/2023-2024 | 2711/TD | 30/10/2023 | 28/12/2025 | TAPAS SANTRA | 938.36 | 0 | 0 | 40
Total | [13 empty] | 1012.01 | 0 | 0