## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 01/11/2022 | B. K. ENTERPRISE | 72.46 | 0 | 0 | 63
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 1661/TD | 03/11/2022 | 03/11/2022 | Resource Division | 239.21 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 611/TD | 17/05/2023 | 17/05/2023 | Resource Division | 31.42 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Contai Saline Area Zone-I (Phase - B) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-I) | Assistant Engineer | Junior Engineer | ORD/000634/2022-2023 | 2313/TD | 05/01/2023 | 28/08/2025 | DAS CONSTRUCTION | 439.86 | 0 | 0 | 42
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II), under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001513/2022-2023 | 357/W/MMD | 09/03/2023 | 05/09/2023 | K.S.P. ENTERPRISE | 13.57 | 0 | 0 | 60
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B), under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001744/2022-2023 | 642/W/MMD | 20/03/2023 | 16/09/2023 | M/S. JIT ENTERPRISE | 13.58 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method with 200 dia UPVC Strainer of 30 M. length all complete including cost of materials for Contai Saline Area Zone-I Water Supply Scheme of Tube Well No.- II within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer |  | ORD/001239/2023-2024 | 1085/TD | 16/03/2024 | 05/04/2024 | RUPKUMAR KARMAKAR | 18.24 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method with 200 dia UPVC Strainer of 30 M. length all complete including cost of materials for Contai Saline Area Zone-I Water Supply Scheme of Tube Well No.- I within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer |  | ORD/001238/2023-2024 | 1086/TD | 16/03/2024 | 05/04/2024 | RUPKUMAR KARMAKAR | 18.4 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I(Phase-A) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | Assistant Engineer | Junior Engineer | ORD/000149/2024-2025 | 1732/CSD | 20/06/2024 | 10/07/2024 | GIRI CONSTRUCTION | 1.16 | 0 | 0 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Supply of documents for way leave permission of Railway Track Between HENRIA-KANTHI Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I(Phase-B) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000147/2024-2025 | 1735/CSD | 20/06/2024 | 10/07/2024 | ABHIJIT BERA | 2.31 | 0 | 0 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Way Leave Plan and Survey Charges under railway track permission for Application ID SER-KGP-2023-WL-136 under Tamluk Division, PHE Dte. |  |  | BILL/00570/2024-2025 | BP-2024-25-236 | 12/07/2024 | 12/07/2024 | FA & CAO, S.E. RAILWAY, GRC. | 0.25 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Payment of wayleave facility charges(SER-KGP-2024-WL-53) |  |  | BILL/00141/2024-2025 | BP-2024-25-84 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.41 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Payment of Wayleave facility charges (SER-KGP-2024-WL-52) |  |  | BILL/00140/2024-2025 | BP-2024-25-83 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.28 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Payment of wayleave facility charges(SER-KGP-2024-WL-49) |  |  | BILL/00137/2024-2025 | BP-2024-25-80 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.59 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | payment of way leave facility cahrges(SER-KGP-2024-WL-51) |  |  | BILL/00139/2024-2025 | BP-2024-25-82 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.3 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Payment of wayleave charges(SER-KGP-2024-WL-50) |  |  | BILL/00138/2024-2025 | BP-2024-25-81 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 9.38 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Electric Quotation for CONTAI S.A. RAJ (PHASE-B) Water Supply Scheme T/W-II,Zone-III, (Ref. ID-204114270) |  |  | BILL/02907/2023-2024 | BP-2023-24-321 | 01/11/2023 | 01/11/2023 | WBSEDCL | 4.72 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Way Leave Plan and Survey Charges under railway track permission for Application ID SER-KGP-2023-WL-136 under Tamluk Division, PHE Dte. |  |  | BILL/01940/2023-2024 | BP-2023-24-894 | 22/02/2024 | 22/02/2024 | FA & CAO, S.E. RAILWAY, GRC. | 0.65 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Contai Saline Area Zone-I ( Phase - B) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-II) | Assistant Engineer | Junior Engineer | ORD/000697/2022-2023 | 2312/TD | 05/01/2023 | 13/01/2025 | DAS CONSTRUCTION | 180.42 | 0 | 0 | 45
20 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Repairing and Renovation of Boundary Wall, Construction of Pump house and allied works of Reservoir (OHR) Site under Augmentation of Contai Saline Area Zone-I ( Phase - B) Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000334/2024-2025 | 3292/TD | 05/10/2024 | 12/07/2025 | DEBANANDA CONSTRUCTION | 21.34 | 0 | 0 | 35
21 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Construction of Pump House & Boundary Wall and others allied works for 1st Tube well site under Contai Saline Area Zone-I (Phase-A) Water Supply Scheme ( Augmentation) in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. (For Low Land) |  |  | ORD/000294/2024-2025 | 3063/TD | 19/09/2024 | 29/10/2024 | GUCHHAIT ENTERPRISE | 14.07 | 0 | 0 | 0
22 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Construction Boundary Wall & Repairing and renovation of Pump House and others allied works for 2nd Tube well site under Contai Saline Area Zone-I (Phase-B) Water Supply scheme ( Augmentation) in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. (For Low Land) |  |  | ORD/000241/2024-2025 | 2680/TD | 22/08/2024 | 01/10/2024 | BISWA NIRMAN ENTERPRISE. | 10.08 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | SM/12364 | Augmentation | Dismantling chlorinator room & Staff quater at Head Work Site/ Reserver site of Contai S.A. Zone I (Phase B) PWSS under Contai Sub Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000282/2024-2025 | 3035/TD | 18/09/2024 | 09/10/2024 | SUBHENDU HAZRA | 3.53 | 0 | 0 | 0
Total | [13 empty] | 1116.23 | 0 | 0