## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS | SM/12398 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MUSTAPHAPUR and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001620/2022-2023 | 507/W/MMD | 20/03/2023 | 31/03/2025 | M/S DILIP MITRA | 22.77 | 0 | 0 | 85
2 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS | SM/12398 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 170.24 | 0.87 | 51
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS | SM/12398 | New | Material Requisition To Resource Division |  |  | RTOR000151/2022-2023 | 2457/TD | 16/01/2023 | 16/01/2023 | Resource Division | 24.12 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS | SM/12398 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Mustaphapur PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000189/2024-2025 | 2199/TD | 09/07/2024 | 19/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
5 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS | SM/12398 | New | Material Requisition To Resource Division |  |  | RTOR000052/2024-2025 | 1660/TD | 29/04/2024 | 29/04/2024 | Resource Division | 11.12 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS | SM/12398 | New | Quotation Bill for New Service connection at T/W NO-I Of MUSTAFAPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004649225/QUOT/03 DT. 20-03-2024 Application NO- 2004649225 Application type-New connection Consumer Id- 204250590 |  |  | BILL/00008/2024-2025 | BP-2024-25-2 | 04/04/2024 | 04/04/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS | SM/12398 | New | Quotation Bill for New Service connection at T/W NO-II Of MUSTAPHAPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886313/QUOT/03/583 DT. 06-09-2024 Application NO- 2004886313 Application type-New connection Consumer Id- 204391660 |  |  | BILL/02452/2024-2025 | C092443181607 | 27/09/2024 | 27/09/2024 | WBSEDCL | 3.54 | 0 | 0 | 0
Total | [13 empty] | 19573.5 | 171.19 | 0.87