## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12399 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAHAT and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001414/2022-2023 | 2425/W/MMD | 31/12/2022 | 31/05/2025 | DEY ENTERPRISE | 22.8 | 0 | 0 | 85
2 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12399 | New | Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1808 nos) under JJM with allied work for Barahat & its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000638/2023-2024 | 2481/TD | 26/09/2023 | 30/05/2026 | MAA ANANDAMAYEE | 547.32 | 149.65 | 27.34 | 35
3 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12399 | New | Material Requisition To Resource Division |  |  | RTOR000323/2022-2023 | 2993/TD | 27/02/2023 | 27/02/2023 | Resource Division | 2.69 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12399 | New | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 30/10/2024 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12399 | New | Quotation Bill for New Service connection at T/W NO-I Of BARAHAT W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769741/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/171 DT. 10-06-2024 Application NO- 2004769741 Application type-New connection Consumer Id- 204327215 |  |  | BILL/01281/2024-2025 | BP-2024-25-336 | 25/06/2024 | 25/06/2024 | WBSEDCL | 5 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12399 | New | Quotation Bill for New Service connection at T/W NO-II Of BARAHAT W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769769/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/170 DT. 10-06-2024 Application NO- 2004769769 Application type-New connection Consumer Id- 204327222 |  |  | BILL/01282/2024-2025 | BP-2024-25-335 | 25/06/2024 | 25/06/2024 | WBSEDCL | 1.2 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12399 | New | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 1641/TD | 18/06/2025 | 18/06/2025 | Resource Division | 11.14 | 0 | 0 | 0
Total | [13 empty] | 651 | 149.65 | 22.99