## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12400 | New | Material Requisition To Resource Division |  |  | RTOR000186/2022-2023 | 2445/TD | 16/01/2023 | 16/01/2023 | Resource Division | 55.25 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12400 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PAHARPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001400/2022-2023 | 2411/W/MMD | 31/12/2022 | 29/06/2023 | SUJOY RANJAN BHOWMICK | 21.62 | 13.57 | 62.77 | 45
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12400 | New | Quotation Bill for New Service connection at T/W NO-I Of PAHARPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743736/QUOT/03 DT. 20-05-2024 Application NO- 2004743736 Application type-New connection Consumer Id- 204312608 |  |  | BILL/01203/2024-2025 | BP-2024-25-320 | 24/06/2024 | 24/06/2024 | WBSEDCL | 6.24 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12400 | New | Material Requisition To Resource Division |  |  | RTOR000035/2024-2025 | 1631/TD | 18/06/2025 | 18/06/2025 | Resource Division | 5.37 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12400 | New | Quotation Bill for New Service connection at T/W NO-II Of PAHARPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004924431/QUOT/03 DT. 01-10-2024 MEMO NO: AMR/NS/436 DT. 01-10-2024 Application NO- 2004924431 Application type-New connection Consumer Id- 204415334 |  |  | BILL/03273/2024-2025 | C122406880068 | 06/12/2024 | 06/12/2024 | WBSEDCL | 4.18 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12400 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 127.31 | 0.65 | 51
Total | [13 empty] | 19600.36 | 140.88 | 0.72