## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | NARAYAN DANRI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12401 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NARAYAN DANRI and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001585/2022-2023 | 468/W/MMD | 20/03/2023 | 16/09/2023 | SOUMEN ELECTRIC | 23.68 | 16.85 | 71.14 | 30
2 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NARAYAN DANRI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12401 | New | Material Requisition To Resource Division |  |  | RTOR000243/2022-2023 | 2723/TD | 06/02/2023 | 06/02/2023 | Resource Division | 15.86 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NARAYAN DANRI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12401 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2046 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of NARAYAN DANRI PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000849/2023-2024 | 72/TD | 05/01/2024 | 25/12/2025 | SRIMANTA KUMAR MAITY | 519.29 | 23.48 | 4.52 | 25
Total | [13 empty] | 558.83 | 40.32 | 7.22