## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12402 | New | Material Requisition To Resource Division |  |  | RTOR000247/2022-2023 | 2721/TD | 06/02/2023 | 06/02/2023 | Resource Division | 19.28 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12402 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHAPUR and ADJOINING MOUJAS, Block ¿ Bhagwanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001412/2022-2023 | 2423/W/MMD | 31/12/2022 | 29/06/2023 | P.K.ENGINEERING | 22.8 | 17.44 | 76.48 | 62
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12402 | New | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 127/TD | 05/01/2024 | 05/01/2024 | Resource Division | 10.28 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12402 | New | Quotation Bill for New Service connection at T/W NO-II Of NILKANTHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE : BHAGWANPUR C.C.C. Ref. Memo No- 2004942161/QUOT/03 DT. 24-10-2024 Application NO- 2004942161 Application type-New connection CONSUMER ID: 204427729 |  |  | BILL/03004/2024-2025 | C112423542425 | 20/11/2024 | 20/11/2024 | WBSEDCL | 2.78 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12402 | New | Quotation Bill for New Service connection at T/W NO-I Of NILKANTHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818541/QUOT/03 DT. 12-07-2024 Application NO- 2004818541 Application type-New connection Consumer Id- 204355510 |  |  | BILL/01890/2024-2025 | BP-2024-25-555 | 08/08/2024 | 08/08/2024 | WBSEDCL | 12.51 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12402 | New | Sinking of Tube Well ,Construction of Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1669 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of NILKANTHAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000076/2023-2024 | 129/TD | 10/04/2023 | 01/12/2025 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 486.76 | 127.04 | 26.1 | 25
7 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/12402 | New | Quotation Bill for New Service connection at T/W NO-II Of NILKANTHAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2005116348/QUOT/03 DT. 06-03-2025 Application NO- 2005116348 Application type-New connection Consumer Id- 204551421 |  |  | BILL/04968/2024-2025 | 42156 | 07/08/2025 | 07/08/2025 | WBSEDCL | 0.88 | 0 | 0 | 0
Total | [13 empty] | 555.28 | 144.47 | 26.02