## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Material Requisition To Resource Division |  |  | RTOR000329/2022-2023 | 2987/TD | 27/02/2023 | 27/02/2023 | Resource Division | 29.7 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(ii)) | Assistant Engineer | Junior Engineer | ORD/000882/2022-2023 | 3239/TD | 15/03/2023 | 29/04/2023 | MAHAPRABHU ENTERPRISE | 9.86 | 2.02 | 20.46 | 21
3 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer | Junior Engineer | ORD/000880/2022-2023 | 3216/TD | 14/03/2023 | 13/05/2023 | THREE MAA ENTERPRISE | 64.69 | 39.91 | 61.69 | 50
4 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(iii)) | Assistant Engineer | Junior Engineer | ORD/000883/2022-2023 | 3240/TD | 15/03/2023 | 05/12/2025 | MODERN CONSTRUCTION | 9.69 | 4.86 | 50.16 | 43
5 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (200 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer | Junior Engineer | ORD/000878/2022-2023 | 3214/TD | 14/03/2023 | 13/04/2023 | G. S. CONSTRUCTION | 34.87 | 26.93 | 77.22 | 79
6 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(iv)) | Assistant Engineer | Junior Engineer | ORD/000255/2023-2024 | 521/TD | 11/05/2023 | 06/09/2025 | PRASANTA MONDAL | 8.09 | 3.41 | 42.16 | 35
7 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C(ii)) | Assistant Engineer | Junior Engineer | ORD/000348/2023-2024 | 877/TD | 01/06/2023 | 01/07/2023 | TARUN KHATUA | 28.18 | 27.54 | 97.73 | 85
8 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (115 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(i)) | Assistant Engineer | Junior Engineer | ORD/000881/2022-2023 | 3238/TD | 15/03/2023 | 29/04/2023 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 9.62 | 9.32 | 96.91 | 100
9 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C(i)) | Assistant Engineer | Junior Engineer | ORD/000347/2023-2024 | 876/TD | 01/06/2023 | 16/07/2023 | TARUN KHATUA | 11.03 | 10.07 | 91.3 | 100
10 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | "G.I pipe column with M.S. Structure for laying of HDPE pipe line with Casing at Kanchanpur Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. " (Total Length= 60.00 mtr, {i) NP-21 to 27= 30.00 mtr + ii) NP-44 to 50= 30.00 mtr .} | Assistant Engineer | Junior Engineer | ORD/001200/2023-2024 | 727/TD | 28/02/2024 | 29/03/2024 | TARUN KHATUA | 8.88 | 8.71 | 98.15 | 100
11 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 115/TD | 05/01/2024 | 05/01/2024 | Resource Division | 10.5 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Quotation for Kanchanpur w/s scheme PH I in the Purba Medinipur under MMD PHE Dte.(Ref ID 204216166, App No 2004599555) |  |  | BILL/04143/2023-2024 | BP-2023-24-755 | 01/03/2024 | 01/03/2024 | WBSEDCL | 5.06 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Quotation for Kanchanpur w/s scheme PH II in the Purba Medinipur under MMD PHE Dte.(Ref ID 204216165, App No 2004599558) |  |  | BILL/04142/2023-2024 | BP-2023-24-756 | 01/03/2024 | 01/03/2024 | WBSEDCL | 3.82 | 0 | 0 | 0
14 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KANCHANPUR and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001583/2022-2023 | 466/W/MMD | 20/03/2023 | 19/09/2025 | DEY ENTERPRISE | 23.7 | 11.15 | 47.04 | 45
15 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000414/2023-2024 | 1099/TD | 08/06/2023 | 01/11/2025 | MAA ANANDAMAYEE | 139.46 | 0 | 0 | 2
16 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Construction of Retaining wall, Approach road & Earth filling Work in Head work site of Kanchanpur Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(length of Retaining wall-120mtr) & (length of Approach road- 60 mtr). | Assistant Engineer | Junior Engineer | ORD/000459/2024-2025 | 3705/TD | 03/12/2024 | 21/06/2025 | TARUN KHATUA | 17.55 | 0 | 0 | 90
17 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | KANCHANPUR AND ADJOINING MOUJAS PWSS | SM/12403 | New | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (280 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | Assistant Engineer | Junior Engineer | ORD/000877/2022-2023 | 3213/TD | 14/03/2023 | 27/12/2024 | SK MAIDUL ISLAM | 39.57 | 25.63 | 64.78 | 60
Total | [13 empty] | 454.29 | 169.57 | 37.33