## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur - I | Tamluk Division | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS | SM/12404 | New | Material Requisition To Resource Division |  |  | RTOR000194/2022-2023 | 2386/TD | 16/01/2023 |  | Resource Division | 13.74 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur - I | Midnapore Mechanical | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS | SM/12404 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DWARIKAPUR and ADJOINING MOUJAS, Block ¿ Bhagwanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001408/2022-2023 | 2419/W/MMD | 31/12/2022 | 29/06/2023 | BOSE & CHATTERJEE INDUSTRIES | 22.76 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Bhagawanpur - I | Tamluk Division | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS | SM/12404 | New | Material Requisition To Resource Division |  |  | RTOR000131/2023-2024 | 85/TD | 05/01/2024 |  | Resource Division | 10.2 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur - I | Tamluk Division | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS | SM/12404 | New | Sinking of Big dia Tube Well, Laying distribution System, Construction of Pump House, Construction of Boundary Wall, Soil investigation, R.C.C. Elevated Reservoir of capacity 200cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation), Accommodate FHTC (1656 nos) & Two years Operation & Maintenance with allied works under JJM for Dwarikapur & It's Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000075/2023-2024 | 128/TD | 10/04/2023 | 07/10/2023 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 407.28 | 0 | 0 | 0
Total | [13 empty] | 453.98 | 0 | 0