## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS | SM/12405 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN KADUA and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002033/2022-2023 | 941/W/MMD | 28/03/2023 | 24/09/2023 | S.G.ENTERPRISE | 21.6 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Deshopran | Tamluk Division | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS | SM/12405 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000492/2023-2024 | 1593/TD | 21/07/2023 | 17/01/2026 | JAYANTA KUMAR MONDAL | 1264.74 | 0 | 0 | 30
3 | PURBA MEDINIPUR | Deshopran | Tamluk Division | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS | SM/12405 | New | Material Requisition To Resource Division |  |  | RTOR000204/2022-2023 | 2406/TD | 16/01/2023 | 16/01/2023 | Resource Division | 18.29 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Deshopran | Tamluk Division | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS | SM/12405 | New | Material Requisition To Resource Division |  |  | RTOR000084/2024-2025 | 2954/TD | 12/09/2024 | 12/09/2024 | Resource Division | 5.5 | 0 | 0 | 0
Total | [13 empty] | 1310.12 | 0 | 0