## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS | SM/12406 | New | Material Requisition To Resource Division |  |  | RTOR000334/2022-2023 | 2981/TD | 27/02/2023 | 27/02/2023 | Resource Division | 22.62 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS | SM/12406 | New | Providing Drilling Crew and other allied works for construction of Tube Well (250mm x 150mm x280 Mtrs. Depth) by utilising Departmental machineries for Dakshin Kalamdan and Sarberya (T/W-I & II) under Purba Medinipur District, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000061/2023-2024 | 854/CDD | 10/07/2023 | 09/08/2023 | MENAKA ENTERPRISE | 31.45 | 13.69 | 43.52 | 100
3 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS | SM/12406 | New | Material Requisition To Resource Division |  |  | RTOR000087/2024-2025 | 2955/TD | 12/09/2024 | 12/09/2024 | Resource Division | 13.47 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS | SM/12406 | New | Dakshin Kalamadan W/S scheme Application No.-2004527976 Ref.-204160990 |  |  | BILL/03265/2023-2024 | BP-2023-24-515 | 09/01/2024 | 09/01/2024 | WBSEDCL | 13.12 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS | SM/12406 | New | Quotation for Dakhin Kalamdan w/s scheme PH II under MMD PHE Dte in the district of Purba Medinipur. (Ref 204221089 App No. 2004606720) |  |  | BILL/04146/2023-2024 | BP-2023-24-757 | 01/03/2024 | 01/03/2024 | WBSEDCL | 2.81 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS | SM/12406 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN KALAMDAN and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001416/2022-2023 | 2427/W/MMD | 31/12/2022 | 26/06/2024 | DEY ENTERPRISE | 23.7 | 22.1 | 93.24 | 48
Total | [13 empty] | 107.16 | 35.78 | 33.39