## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-J ) | Assistant Engineer | Junior Engineer | ORD/000863/2022-2023 | 3178/TD | 10/03/2023 | 25/03/2023 | M/S SOURAV MAHAPATRA | 2.72 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Material Requisition To Resource Division |  |  | RTOR000156/2022-2023 | 2463/TD | 16/01/2023 | 16/01/2023 | Resource Division | 60.63 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-I ) | Assistant Engineer | Junior Engineer | ORD/000860/2022-2023 | 3177/TD | 10/03/2023 | 25/03/2023 | DAS ENTERPRISE. | 9.58 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-D) | Assistant Engineer | Junior Engineer | ORD/000857/2022-2023 | 3174/TD | 10/03/2023 | 16/02/2026 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.84 | 0 | 0 | 97
5 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-E) | Assistant Engineer | Junior Engineer | ORD/000858/2022-2023 | 3175/TD | 10/03/2023 | 16/02/2026 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.83 | 0 | 0 | 97
6 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-H ) | Assistant Engineer | Junior Engineer | ORD/000859/2022-2023 | 3176/TD | 10/03/2023 | 25/03/2023 | CHARUBALA ENTERPRISE | 9.93 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-F ) | Assistant Engineer | Junior Engineer | ORD/000072/2023-2024 | 174/TD | 11/04/2023 | 26/04/2023 | AURGHA BHATTACHARYA | 9.97 | 0 | 0 | 100
8 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-G) | Assistant Engineer | Junior Engineer | ORD/000370/2023-2024 | 1006/TD | 05/06/2023 | 20/06/2023 | MAHAMAYA TIMBER AND CONSTRUCTION | 9.96 | 0 | 0 | 96
9 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying of Balance Distribution HDPE Pipe Line(180 mm dia) for Dakshin Shitala Piped Water Supply Scheme due to Revised drawing within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000707/2023-2024 | 2873/TD | 17/11/2023 | 07/12/2023 | HYDROTECH ASSOCIATES | 11.34 | 0 | 0 | 99
10 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Land development of 2nd T/W Site at Dakshin Shitala & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000247/2024-2025 | 872/DSD | 27/08/2024 | 03/09/2024 | ABHIJIT BERA | 0.91 | 0 | 0 | 100
11 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 92/TD | 05/01/2024 | 05/01/2024 | Resource Division | 6.28 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Quotation Bill for New Service connection at T/W NO-I Of DAKSHIN SHITALA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004905806/QUOT/03 DT. 18-09-2024 Application NO- 2004905806 Application type-New connection Consumer Id- 204402411 |  |  | BILL/02498/2024-2025 | C102415718521 | 05/10/2024 | 05/10/2024 | WBSEDCL | 7.48 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Quotation Bill for New Service connection at T/W NO-II Of DAKSHIN SHITALA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670651/QUOT/03 DT. 05-04-2024 Application NO- 2004670651 Application type-New connection Consumer Id- 204266386 |  |  | BILL/00296/2024-2025 | BP-2024-25-49 | 18/04/2024 | 18/04/2024 | WBSEDCL | 7.85 | 0 | 0 | 0
14 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying distribution pipe line, & Accommodate FHTC ( 128Nos) under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | Assistant Engineer | Junior Engineer | ORD/000855/2022-2023 | 3173/TD | 10/03/2023 | 01/05/2026 | DHANANJOY DAS | 39.79 | 0 | 0 | 60
15 | PURBA MEDINIPUR | Ramnagar-II | Central Drilling | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
16 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, & Accommodate FHTC ( 500Nos) under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | Assistant Engineer | Junior Engineer | ORD/000410/2023-2024 | 1096/TD | 08/06/2023 | 24/02/2026 | ABHIJIT BERA | 119.92 | 0 | 0 | 48
17 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | SM/12407 | New | Laying distribution pipe line, soil investigation, 150 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 392 Nos) under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | Assistant Engineer | Junior Engineer | ORD/000629/2023-2024 | 2437/TD | 19/09/2023 | 12/03/2025 | EVEREST INFRATECH INC | 119.98 | 0 | 0 | 30
Total | [13 empty] | 21795.76 | 0 | 0