## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12428 | New | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (618 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Purba Puroshattampur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000353/2023-2024 | 880/TD | 01/06/2023 | 28/11/2023 | BARH CONSTRUCTION | 281.85 | 169.52 | 60.15 | 66
2 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12428 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBO PURUSHOTTAMPUR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001647/2022-2023 | 541/W/MMD | 20/03/2023 | 31/08/2024 | SOUMEN ELECTRIC | 21.56 | 19.72 | 91.46 | 80
3 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12428 | New | Material Requisition To Resource Division |  |  | RTOR000265/2022-2023 | 2692/TD | 06/02/2023 | 06/02/2023 | Resource Division | 14.58 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12428 | New | Purushottampur W/S scheme PH-I Application no.-2004522734 ref.-204156888 |  |  | BILL/03197/2023-2024 | BP-2023-24-472 | 27/12/2023 | 27/12/2023 | WBSEDCL | 2.75 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12428 | New | Purushottampur W/S scheme PH-II Application no.-2004522748 ref.-204156889 |  |  | BILL/03198/2023-2024 | BP-2023-24-471 | 27/12/2023 | 27/12/2023 | WBSEDCL | 2.78 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12428 | New | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 98/TD | 05/01/2024 | 05/01/2024 | Resource Division | 3.81 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12428 | New | Additional Quotation Bill for New Service connection at T/W NO-I & II Of PURBA PURUSHOTTAMPUR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- PBN/SM/958 DT. 28-02-2024 Application NO- T/W NO-I: 2004522734 Con. Id- 204156888 ( T/W NO-I) Application NO- T/W NO-II: 2004522748 Con. Id- 204156889 ( T/W NO-II) |  |  | BILL/04267/2023-2024 | BP-2023-24-795 | 06/03/2024 | 06/03/2024 | WBSEDCL | 3.26 | 0 | 0 | 0
Total | [13 empty] | 330.59 | 189.24 | 57.24