## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | BAGMARI AND IT'S ADJOINING MOUJAS PWSS | SM/12429 | New | Material Requisition To Resource Division |  |  | RTOR000267/2022-2023 | 2700/TD | 06/02/2023 | 06/02/2023 | Resource Division | 46.45 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | BAGMARI AND IT'S ADJOINING MOUJAS PWSS | SM/12429 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 200 Cum Capacity OHR ( Intze type with pile foundatio ) & Accommodate FHTC ( 1230 Nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Bagmari & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000180/2023-2024 | 294/TD | 20/04/2023 | 17/10/2023 | BASANTA KUMAR MAITY | 401.59 | 256.63 | 63.9 | 63
3 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | BAGMARI AND IT'S ADJOINING MOUJAS PWSS | SM/12429 | New | Sinking of 250mm x 150mm dia Tube well of 210 mtr deep tubewell Drilling by Direct Rotary method with 150 dia.uPVC. Strainer of 30m.length all complete including cost of materials for Replacement of 2nd Tubewell at Bagmari & its adjoining mouzas Water Supply Scheme within Egra- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000116/2024-2025 | 1913/TD | 07/06/2024 | 27/06/2024 | MAITY CONSTRUCTION | 12.06 | 10.45 | 86.67 | 100
4 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | BAGMARI AND IT'S ADJOINING MOUJAS PWSS | SM/12429 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 79/TD | 05/01/2024 | 05/01/2024 | Resource Division | 7.58 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | BAGMARI AND IT'S ADJOINING MOUJAS PWSS | SM/12429 | New | Electric Quotation for BAGMARI (RAMNAGAR-I) Water Supply Scheme T/W-I, (Ref. ID-204134070) |  |  | BILL/03001/2023-2024 | BP-2023-24-358 | 24/11/2023 | 24/11/2023 | WBSEDCL | 4.02 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | BAGMARI AND IT'S ADJOINING MOUJAS PWSS | SM/12429 | New | Electric Quotation for BAGMARI (RAMNAGAR-I) Water Supply Scheme T/W-II, (Ref. ID-204143154) |  |  | BILL/03055/2023-2024 | BP-2023-24-376 | 02/12/2023 | 02/12/2023 | WBSEDCL | 4.91 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | BAGMARI AND IT'S ADJOINING MOUJAS PWSS | SM/12429 | New | Laying of balance distribution pipe line to provide Balance FHTC with allied works for Bagmari & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHE Dte, Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000596/2024-2025 | 568/TD | 17/02/2025 | 08/04/2025 | MAITY CONSTRUCTION | 23.23 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | BAGMARI AND IT'S ADJOINING MOUJAS PWSS | SM/12429 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAGMARI and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001687/2022-2023 | 560/W/MMD | 20/03/2023 | 31/05/2024 | M/S B.M. ELECTRICAL | 22.81 | 21.13 | 92.66 | 10
Total | [13 empty] | 522.64 | 288.22 | 55.15