## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | PADIMA AND ADJOINING MOUJAS PWSS | SM/12430 | New | Sinking of Tube Well, Rising main ,Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 150Cum OHR ( Intze type with pile foundatio ) Pipe Carrying canal crossing Structure & Accommodate FHTC ( 960 Nos) Including 2 years of Operation & Maintenance under JJM with allied work for Padima & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000548/2023-2024 | 1987/TD | 21/08/2023 | 30/06/2026 | ONKAR ENTERPRISE | 339.12 | 210.05 | 61.94 | 50
2 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | PADIMA AND ADJOINING MOUJAS PWSS | SM/12430 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PADIMA and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001665/2022-2023 | 548/W/MMD | 20/03/2023 | 09/03/2025 | DEBJYOTI BASU | 21.62 | 19.87 | 91.94 | 100
3 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | PADIMA AND ADJOINING MOUJAS PWSS | SM/12430 | New | Material Requisition To Resource Division |  |  | RTOR000311/2022-2023 | 2998/TD | 27/02/2023 | 27/02/2023 | Resource Division | 23.63 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | PADIMA AND ADJOINING MOUJAS PWSS | SM/12430 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Padima PWSS at Ramnagar - I Block under Tamluk Division,PHE Dte. |  |  | ORD/000883/2023-2024 | 205/TD | 10/01/2024 | 20/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
5 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | PADIMA AND ADJOINING MOUJAS PWSS | SM/12430 | New | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 99/TD | 05/01/2024 | 05/01/2024 | Resource Division | 5.91 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | PADIMA AND ADJOINING MOUJAS PWSS | SM/12430 | New | Quotation Bill for New Service connection at T/W NO-II Of PADIMA W/S Scheme under MMD, PHE, Dte. Block- Ramnagar-I, DIGHA C.C.C. Ref. Memo No- 2004626606/QUOT/03 DT. 04-03-2024 Application NO- 2004626606 Application type-New connection CONSUMMER ID- 204233354 |  |  | BILL/04338/2023-2024 | BP-2023-24-804 | 11/03/2024 | 11/03/2024 | WBSEDCL | 7.74 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | PADIMA AND ADJOINING MOUJAS PWSS | SM/12430 | New | PADIMA W/S SCHEME T/W-I Application No.-2004566513 Ref.-204194520 |  |  | BILL/03532/2023-2024 | BP-2023-24-613 | 07/02/2024 | 07/02/2024 | WBSEDCL | 6.31 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | PADIMA AND ADJOINING MOUJAS PWSS | SM/12430 | New | Surging of existing 2nd Tube site of Padima W/S Scheme within Ramnagar-I Block under Digha Sub-Division, of Tamluk Diision P.H.E.Dte. Purba Medinipur. |  | Junior Engineer | ORD/000041/2025-2026 | 41/DSD | 11/04/2025 | 18/04/2025 | ONKAR ENTERPRISE | 0.61 | 0 | 0 | 100
Total | [13 empty] | 405.89 | 230.88 | 56.88