## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS | SM/12431 | New | Material Requisition To Resource Division |  |  | RTOR000336/2022-2023 | 2979/TD | 27/02/2023 | 27/02/2023 | Resource Division | 17 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS | SM/12431 | New | Material Requisition To Resource Division |  |  | RTOR000081/2024-2025 | 2953/TD | 12/09/2024 | 12/09/2024 | Resource Division | 14.49 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS | SM/12431 | New | Quotation for New service connection at Chingurdaniya w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004620601 , Ref ID 204229471) |  |  | BILL/04330/2023-2024 | BP-2023-24-812 | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.19 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS | SM/12431 | New | Chingurdania W/S scheme PH No.-I Application No.-2004565714 Ref.-204193544 |  |  | BILL/03477/2023-2024 | BP-2023-24-594 | 02/02/2024 | 02/02/2024 | WBSEDCL | 3.68 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS | SM/12431 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 42.76 | 0.2 | 11
6 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS | SM/12431 | New | Tube well, Pump House, 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2353 nos) under JJM with allied work for Chingur Dania- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. | Assistant Engineer | Junior Engineer | ORD/000479/2023-2024 | 1552/TD | 19/07/2023 | 01/12/2025 | DAS ENTERPRISE | 764.26 | 293.31 | 38.38 | 70
Total | [13 empty] | 22142.38 | 336.07 | 1.52