## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur - I | Tamluk Division | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Material Requisition To Resource Division |  |  | RTOR000325/2022-2023 | 2991/TD | 27/02/2023 |  | Resource Division | 14.06 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur - I | Midnapore Mechanical | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TALCHITKINI and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001643/2022-2023 | 520/W/MMD | 20/03/2023 | 16/09/2023 | BIJAN ENTERPRISE | 22.72 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur - I | Tamluk Division | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Sinking of Tube well,Pump House ,Construction of 200 cum & 250 Cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3146 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Dhankar & Talchitkini its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000495/2023-2024 | 1671/TD | 25/07/2023 | 21/01/2024 | HALDIA DEVELOPMENT CONSTRUCTION | 895.07 | 0 | 0 | 20
Total | [13 empty] | 931.86 | 0 | 0