## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TALCHITKINI and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001643/2022-2023 | 520/W/MMD | 20/03/2023 | 16/09/2023 | BIJAN ENTERPRISE | 22.72 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Sinking of Tube well,Pump House ,Construction of 200 cum & 250 Cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3146 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Dhankar & Talchitkini its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000495/2023-2024 | 1671/TD | 25/07/2023 | 30/05/2026 | HALDIA DEVELOPMENT CONSTRUCTION | 895.07 | 0 | 0 | 20
3 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Material Requisition To Resource Division |  |  | RTOR000325/2022-2023 | 2991/TD | 27/02/2023 | 27/02/2023 | Resource Division | 14.06 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 30/10/2024 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Material Requisition To Resource Division |  |  | RTOR000041/2024-2025 | 1626/TD | 18/06/2025 | 18/06/2025 | Resource Division | 11.29 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Quotation Bill for New Service connection at T/W NO-I Of TALCHITKINI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2005238766/QUOT/03 DT. 23-05-2025 MEMO NO: AMR/PHE/261 DT. 23-05-2025 Application NO- 2005238766 Application type-New connection Consumer Id- 204631508 |  |  | BILL/00901/2025-2026 | W/267/25-26 | 07/08/2025 | 07/08/2025 | WBSEDCL | 5.57 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Quotation Bill for New Service connection at T/W NO-II Of TALCHITKINI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2005238834/QUOT/03 DT. 23-05-2025 MEMO NO: AMR/PHE/260 DT. 23-05-2025 Application NO- 2005238834 Application type-New connection Consumer Id- 204631502 |  |  | BILL/00902/2025-2026 |  | 02/06/2025 | 02/06/2025 | WBSEDCL | 9.07 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | SM/12433 | New | Shifting of hanging electrical cable of adjacent public building over Talchitkini 2nd pump hose site, Ref. ID : 860325204 Application ID: 100000129374, Date-31.01.2025 |  |  | BILL/00087/2025-2026 |  | 08/04/2025 | 08/04/2025 | WBSEDCL | 0.17 | 0 | 0 | 0
Total | [13 empty] | 1018.82 | 0 | 0