## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS | SM/12434 | New | Material Requisition To Resource Division |  |  | RTOR000275/2022-2023 | 2699/TD | 06/02/2023 | 06/02/2023 | Resource Division | 20.82 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS | SM/12434 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MUKUNDAPUR and ADJOINING MOUJAS, Block - Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001638/2022-2023 | 518/W/MMD | 20/03/2023 | 16/09/2023 | RMD TRADING | 22.76 | 0 | 0 | 85
3 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS | SM/12434 | New | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 118/TD | 05/01/2024 | 05/01/2024 | Resource Division | 7.8 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS | SM/12434 | New | Quotation Bill for New Service connection at T/W NO-I Of PURBA MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738920/QUOT/03 DT. 17-05-2024 Application NO- LY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738920 Application type-New connection Consumer Id- 204309716 |  |  | BILL/01096/2024-2025 | BP-2024-25-225 | 31/05/2024 | 31/05/2024 | WBSEDCL | 4.96 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS | SM/12434 | New | Quotation Bill for New Service connection at T/W NO-II Of PURBA MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004720948/QUOT/03 DT. 07-05-2024 Application NO- 2004720948 Application type-New connection Consumer Id- 204298864 |  |  | BILL/00444/2024-2025 | BP-2024-25-171 | 07/06/2024 | 07/06/2024 | WBSEDCL | 36.92 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS | SM/12434 | New | Sinking of Tube Well ,Construction of 250 Cu.m. Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2852 Nos) For 2 nos Pipe Water Supply Scheme including (Santra & Purba Mukundapur) including two years Operation & Maintainance within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000682/2023-2024 | 2711/TD | 30/10/2023 | 28/12/2025 | TAPAS SANTRA | 938.36 | 0 | 0 | 40
Total | [13 empty] | 1031.62 | 0 | 0