## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 280 mtrs. Depth) by utilising Departmental machineries for Tikashi W/S Scheme (TW-III), Khejuri-I block under Purba Midnapore District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000009/2023-2024 | 21/CDD | 04/04/2023 | 04/05/2023 | MENAKA ENTERPRISE | 15.48 | 12.17 | 78.61 | 100
2 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Providing drilling crew and other allied works for construction of Tube Well (250 mm X 150mm X 280mm Depth) by utilising Departmental Machineries for Tikashi W/S Scheme(TW-I), Khejuri-I Block under Purba Medinipur District, CDD,P.H.E.Dte. | Driller In Charge | Junior Engineer | ORD/000025/2023-2024 | 850/CDD | 10/07/2023 | 09/08/2023 | UNIVERSAL ENTERPRISES | 15.71 | 12.88 | 81.93 | 100
3 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Material Requisition To Resource Division |  |  | RTOR000337/2022-2023 | 2978/TD | 27/02/2023 | 27/02/2023 | Resource Division | 42.38 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Electric Quotation for TIKASHI, Water Supply Scheme T/W-II, (Ref. ID-204049560) |  |  | BILL/01681/2023-2024 | BP-2023-24-161 | 04/08/2023 | 04/08/2023 | WBSEDCL | 2.41 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Instalation of display Board at different work site of Tikashi & Adjoining Moujas New PWSS in Khejuri-I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001175/2023-2024 | 2330/CSD | 29/12/2023 | 05/01/2024 | M/S. NEW DINDA ENTERPRISE | 0.21 | 0.21 | 100 | 100
6 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Material Requisition To Resource Division |  |  | RTOR000065/2024-2025 | 2979/TD | 12/09/2024 | 12/09/2024 | Resource Division | 15.26 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Electric Quotation for TIKASHI Water Supply Scheme T/W-I, (Ref. ID-204134790) |  |  | BILL/03185/2023-2024 | BP-2023-24-440 | 19/12/2023 | 19/12/2023 | WBSEDCL | 5.13 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Additional quotation for Tkashi w/s swcheme PH I at Khejuri I Block in the District of Purba Medinipur under MMD PHE Dte. (Application ID 100000100192 Dated 12.02.2024 Ref ID 860292212) |  |  | BILL/03783/2023-2024 | BP-2023-24-715 | 20/02/2024 | 20/02/2024 | WBSEDCL | 0.84 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line, Boundary Wall, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-V) | Assistant Engineer | Junior Engineer | ORD/000144/2023-2024 | 272/TD | 20/04/2023 | 19/06/2023 | MRINAL KANTI PRADHAN | 61.5 | 41.07 | 66.77 | 60
10 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VI) | Assistant Engineer | Junior Engineer | ORD/000146/2023-2024 | 273/TD | 20/04/2023 | 26/04/2025 | PARIA ENTERPRISE | 38.1 | 23.31 | 61.2 | 65
11 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VII) | Assistant Engineer | Junior Engineer | ORD/000147/2023-2024 | 274/TD | 20/04/2023 | 15/05/2023 | DEBABRATA DAS | 10.89 | 7.92 | 72.78 | 74
12 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VIII) | Assistant Engineer | Junior Engineer | ORD/000148/2023-2024 | 275/TD | 20/04/2023 | 26/04/2025 | PARIA ENTERPRISE | 46.77 | 39.65 | 84.78 | 85
13 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-III) | Assistant Engineer | Junior Engineer | ORD/000134/2023-2024 | 271/TD | 20/04/2023 | 12/10/2025 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 97.2 | 56.76 | 58.4 | 60
14 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-IX) | Assistant Engineer | Junior Engineer | ORD/000383/2023-2024 | 1007/TD | 05/06/2023 | 30/06/2023 | DEBABRATA DAS | 14.02 | 9.94 | 70.87 | 73
15 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Pump House , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-II) | Assistant Engineer | Junior Engineer | ORD/000257/2023-2024 | 537/TD | 12/05/2023 | 24/03/2026 | GIRI CONSTRUCTION | 139.39 | 111.43 | 79.94 | 80
16 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-IV) | Assistant Engineer | Junior Engineer | ORD/000242/2023-2024 | 509/TD | 11/05/2023 | 25/06/2023 | B M ENTERPRISE | 81.75 | 40.93 | 50.07 | 60
17 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Trial boring of 100 mm x 50 mm dia x 280 mtr (av.) depth Tube well & sinking upto 200 mtr. depth with PVC pipes including cost of all materials for Tikashi PWSS ( 2nd TW Site) under Contai Sub Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000209/2024-2025 | 2383/TD | 26/07/2024 | 10/08/2024 | BISWA NIRMAN ENTERPRISE. | 2.16 | 2.03 | 94.09 | 100
18 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Balance portion of dismantling, cement concrete and construction of sluice valve including supply of 100 mm dia GI pipe for laying of Distribution pipe line by HDPE pipes with allied works of TIKASHI- PWSS in Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-VIII) | Assistant Engineer | Junior Engineer | ORD/000460/2024-2025 | 2444/CSD | 22/10/2024 | 12/11/2024 | ROZE SEKH | 0.94 | 0 | 0 | 100
19 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TIKASHI and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000090/2023-2024 | 1266/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 25.14 | 22.33 | 88.82 | 88
20 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Pump House,350 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-I) | Assistant Engineer | Junior Engineer | ORD/000385/2023-2024 | 1043/TD | 07/06/2023 | 26/06/2026 | TAPAS SANTRA | 245.15 | 134.79 | 54.98 | 85
Total | [13 empty] | 860.43 | 515.42 | 59.9