## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 280 mtrs. Depth) by utilising Departmental machineries for Tikashi W/S Scheme (TW-III), Khejuri-I block under Purba Midnapore District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000009/2023-2024 | 21/CDD | 04/04/2023 | 04/05/2023 | MENAKA ENTERPRISE | 15.48 | 0 | 0 | 100
2 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Providing drilling crew and other allied works for construction of Tube Well (250 mm X 150mm X 280mm Depth) by utilising Departmental Machineries for Tikashi W/S Scheme(TW-I), Khejuri-I Block under Purba Medinipur District, CDD,P.H.E.Dte. | Driller In Charge | Junior Engineer | ORD/000025/2023-2024 | 850/CDD | 10/07/2023 | 09/08/2023 | UNIVERSAL ENTERPRISES | 15.71 | 0 | 0 | 100
3 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Material Requisition To Resource Division |  |  | RTOR000337/2022-2023 | 2978/TD | 27/02/2023 | 27/02/2023 | Resource Division | 42.38 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Electric Quotation for TIKASHI, Water Supply Scheme T/W-II, (Ref. ID-204049560) |  |  | BILL/01681/2023-2024 | BP-2023-24-161 | 04/08/2023 | 04/08/2023 | WBSEDCL | 2.41 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Instalation of display Board at different work site of Tikashi & Adjoining Moujas New PWSS in Khejuri-I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001175/2023-2024 | 2330/CSD | 29/12/2023 | 05/01/2024 | M/S. NEW DINDA ENTERPRISE | 0.21 | 0 | 0 | 100
6 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Material Requisition To Resource Division |  |  | RTOR000065/2024-2025 | 2979/TD | 12/09/2024 | 12/09/2024 | Resource Division | 15.26 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Electric Quotation for TIKASHI Water Supply Scheme T/W-I, (Ref. ID-204134790) |  |  | BILL/03185/2023-2024 | BP-2023-24-440 | 19/12/2023 | 19/12/2023 | WBSEDCL | 5.13 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Additional quotation for Tkashi w/s swcheme PH I at Khejuri I Block in the District of Purba Medinipur under MMD PHE Dte. (Application ID 100000100192 Dated 12.02.2024 Ref ID 860292212) |  |  | BILL/03783/2023-2024 | BP-2023-24-715 | 20/02/2024 | 20/02/2024 | WBSEDCL | 0.84 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line, Boundary Wall, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-V) | Assistant Engineer | Junior Engineer | ORD/000144/2023-2024 | 272/TD | 20/04/2023 | 19/06/2023 | MRINAL KANTI PRADHAN | 61.5 | 0 | 0 | 60
10 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VI) | Assistant Engineer | Junior Engineer | ORD/000146/2023-2024 | 273/TD | 20/04/2023 | 26/04/2025 | PARIA ENTERPRISE | 38.1 | 0 | 0 | 65
11 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VII) | Assistant Engineer | Junior Engineer | ORD/000147/2023-2024 | 274/TD | 20/04/2023 | 15/05/2023 | DEBABRATA DAS | 10.89 | 0 | 0 | 74
12 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VIII) | Assistant Engineer | Junior Engineer | ORD/000148/2023-2024 | 275/TD | 20/04/2023 | 26/04/2025 | PARIA ENTERPRISE | 46.77 | 0 | 0 | 85
13 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-III) | Assistant Engineer | Junior Engineer | ORD/000134/2023-2024 | 271/TD | 20/04/2023 | 13/08/2025 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 97.2 | 0 | 0 | 60
14 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TIKASHI and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000090/2023-2024 | 1266/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 25.14 | 0 | 0 | 88
15 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-IX) | Assistant Engineer | Junior Engineer | ORD/000383/2023-2024 | 1007/TD | 05/06/2023 | 30/06/2023 | DEBABRATA DAS | 14.02 | 0 | 0 | 73
16 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Pump House , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-II) | Assistant Engineer | Junior Engineer | ORD/000257/2023-2024 | 537/TD | 12/05/2023 | 24/03/2026 | GIRI CONSTRUCTION | 139.39 | 0 | 0 | 80
17 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | SM/12482 | New | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-IV) | Assistant Engineer | Junior Engineer | ORD/000242/2023-2024 | 509/TD | 11/05/2023 | 25/06/2023 | B M ENTERPRISE | 81.75 | 0 | 0 | 60
Total | [13 empty] | 612.18 | 0 | 0