## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Tamluk Division | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. | SM/12483 | New | Material Requisition To Resource Division |  |  | RTOR000317/2022-2023 | 2972/TD | 27/02/2023 | 27/02/2023 | Resource Division | 65.15 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. | SM/12483 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAGDA and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001398/2022-2023 | 2409/W/MMD | 31/12/2022 | 29/06/2023 | SUJOY RANJAN BHOWMICK | 21.62 | 13.57 | 62.77 | 45
3 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. | SM/12483 | New | Quotation Bill for New Service connection at T/W NO-I Of KHAGDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004852019/QUOT/03/563 DT. 07-08-2024 Application NO- 2004852019 Application type-New connection Consumer Id- 204373372 |  |  | BILL/02124/2024-2025 | C082449401206 | 02/09/2024 | 02/09/2024 | WBSEDCL | 5.03 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-II | Tamluk Division | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. | SM/12483 | New | Sinking of Tube Well ,Rising main ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , OHR (Intze type with pile foundation) & Accommodate FHTC (5135 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dubda & Khagda PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000511/2023-2024 | 1733/TD | 31/07/2023 | 27/10/2025 | MAHAVIR PUMPS MFG. PVT. LTD. | 1235.52 | 97.49 | 7.89 | 48
Total | [13 empty] | 1327.33 | 111.06 | 8.37