## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. | SM/12484 | New | Material Requisition To Resource Division |  |  | RTOR000324/2022-2023 | 2992/TD | 27/02/2023 | 27/02/2023 | Resource Division | 26.09 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. | SM/12484 | New | Sinking of Tube well,Pump House ,Construction of 200 cum & 250 Cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3146 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Dhankar & Talchitkini its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000495/2023-2024 | 1671/TD | 25/07/2023 | 01/12/2025 | HALDIA DEVELOPMENT CONSTRUCTION | 895.07 | 0 | 0 | 20
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. | SM/12484 | New | Quotation Bill for New Service connection at T/W NO-I Of DHANKAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004607668/QUOT/03 DT. 21-02-2024 Application NO- 2004607668 Application type-New connection Consumer Id- 204222374 |  |  | BILL/04387/2023-2024 | BP-2023-24-825 | 13/03/2024 | 13/03/2024 | WBSEDCL | 4.29 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. | SM/12484 | New | Quotation Bill for New Service connection at T/W NO-II Of DHANKAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743815/QUOT/03 DT. 20-05-2024 Application NO- 2004743815 Application type-New connection Consumer Id- 204312604 |  |  | BILL/01205/2024-2025 | BP-2024-25-321 | 24/06/2024 | 24/06/2024 | WBSEDCL | 3.12 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. | SM/12484 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DHANKAR and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001634/2022-2023 | 515/W/MMD | 20/03/2023 | 01/06/2025 | KARUNAMOY ENGINEERING | 22.75 | 0 | 0 | 51
Total | [13 empty] | 951.33 | 0 | 0