## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS | SM/12485 | Augmentation | Laying of Distribution System to accomodate FHTC (3086 Nos) for Augmentation of Ramnagar Water Supply Scheme (Zone-I) within Ramnagar-I Block under Tamluk Division in the district of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000742/2022-2023 | 2533/TD | 19/01/2023 | 19/04/2023 | BASANTA KUMAR MAITY | 287.99 | 125.94 | 43.73 | 45
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ramnagar (Zone-I) PWSS | SM/12485 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ramnagar (Zone-I) PWSS, Block Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001916/2022-2023 | 820/W/MMD | 24/03/2023 | 31/07/2025 | M/S SWAPAN BANERJEE | 27.17 | 0 | 0 | 52
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS | SM/12485 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000236/2022-2023 | 2613/TD | 02/02/2023 | 02/02/2023 | Resource Division | 75.91 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS | SM/12485 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000286/2022-2023 | 2639/TD | 02/02/2023 | 02/02/2023 | Resource Division | 19.01 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS | SM/12485 | Augmentation | Construction of Pump House, Boundary Wall, Laying of Rising main with distribution pipe line & Accommodate FHTC ( 500 Nos) under JJM with allied work for Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000858/2023-2024 | 169/TD | 09/01/2024 | 23/02/2024 | BASANTA KUMAR MAITY | 104.58 | 38.48 | 36.8 | 41
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS | SM/12485 | Augmentation | Sinking of 300 mm. x 200 mm. dia. x 270 mtr. deep tube well by direct rotary rig method for 3rd tubewell Site of Ramnagar Zone-I Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001247/2023-2024 | 1079/TD | 16/03/2024 | 14/10/2024 | PRANTIK DRILLING AGENCY | 19.83 | 3.27 | 16.51 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS | SM/12485 | Augmentation | Laying of Distribution Pipe Line for Balance 180 mm dia HDPE pipe( N.P-72-74(P)=18.0M, 53-72=298.0M, 34-53(P)=53.0M) within Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme of Ramnagar-I Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001221/2023-2024 | 1032/TD | 15/03/2024 | 29/04/2024 | APARNA CONSTRUCTION | 4.72 | 4.72 | 100 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS | SM/12485 | Augmentation | Laying of Distribution Pipe Line for Balance 180 mm dia HDPE pipe( N.P- 34-53(P)=233.0M, 26-34=136.0M) within Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme of Ramnagar-I Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001223/2023-2024 | 1033/TD | 15/03/2024 | 29/04/2024 | BASANTI ENTERPRISE | 4.69 | 4.67 | 99.54 | 100
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ramnagar (Zone-I) PWSS | SM/12485 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-I Of RAMNAGAR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004957544/QUOT/03 DT. 06-11-2024 Application NO- 2004957544 Application type-New connection Consumer Id- 204440003 |  |  | BILL/03008/2024-2025 | C112423558120 | 19/11/2024 | 19/11/2024 | WBSEDCL | 2.66 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-I) PWSS | SM/12485 | Augmentation | Renovation & Repairing of existing pump house - II at 2nd tube well site of Ramnagar Zone-I W/S Scheme within Ramnagar-I Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  | Junior Engineer | ORD/000531/2024-2025 | 1316/DSD | 13/01/2025 | 20/01/2025 | PURNENDU MAITY | 0.94 | 0 | 0 | 100
Total | [13 empty] | 547.49 | 177.08 | 32.34