## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ramnagar (Zone-II) PWSS | SM/12486 | Augmentation | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 280 Mtrs. Depth) by utilising Departmental Machineries for Ramnagar W/S Scheme (TW-I, Z-II) Ramnagar-I Block under Purba Medinipur District, Central Drilling Division, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000031/2023-2024 | 454/CDD | 02/06/2023 | 02/07/2023 | UNIVERSAL ENTERPRISES | 20.47 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-II) PWSS | SM/12486 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000287/2022-2023 | 2640/TD | 02/02/2023 | 02/02/2023 | Resource Division | 18.12 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-II) PWSS | SM/12486 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000237/2022-2023 | 2614/TD | 02/02/2023 | 02/02/2023 | Resource Division | 65.04 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ramnagar (Zone-II) PWSS | SM/12486 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ramnagar (Zone-II) PWSS, Block Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001917/2022-2023 | 821/W/MMD | 24/03/2023 | 20/09/2023 | M/S SWAPAN BANERJEE | 27.17 | 0 | 0 | 45
5 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ramnagar (Zone-II) PWSS | SM/12486 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II(D),CDD P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000091/2023-2024 | 227/CMSD-II(D) | 10/10/2023 | 10/12/2023 | DILIP KAR | 0.29 | 0 | 0 | 50
6 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ramnagar (Zone-II) PWSS | SM/12486 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Ramnagar W/S Scheme (Z- II,T/W-II) , Ramnagar-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000133/2023-2024 | 544/CDD | 02/06/2023 | 22/07/2024 | UNIVERSAL ENTERPRISES | 20.47 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ramnagar (Zone-II) PWSS | SM/12486 | Augmentation | Ramnagar W/S scheme T/W-I, Zone-II Application-2004536109 Ref.-204168170 |  |  | BILL/03289/2023-2024 | BP-2023-24-541 | 11/01/2024 | 11/01/2024 | WBSEDCL | 5.06 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-II) PWSS | SM/12486 | Augmentation | Laying of Distribution System to accomodate FHTC(2941 Nos), Construction of Boundary Wall,Pump House ,R.C.C. Overhead Reservoir of Capacity 350 Cum and staging height 20 meter for Augmentation of Ramnagar Water Supply Scheme (Zone-II) within Ramnagar-I Block under Tamluk Division in the district of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000743/2022-2023 | 2532/TD | 19/01/2023 | 01/04/2025 | BASANTA KUMAR MAITY | 476.59 | 0 | 0 | 66
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ramnagar (Zone-II) PWSS | SM/12486 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Ramnagar Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000638/2022-2023 | 741/TD | 04/07/2022 | 24/07/2022 | SANTRA ENTERPRISE. | 4.52 | 0 | 0 | 100
Total | [13 empty] | 637.72 | 0 | 0