## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Amarshikashba Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000321/2022-2023 | 591/TD | 17/06/2022 | 07/07/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 3.71 | 87.28 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2022-2023 | 1668/TD | 03/11/2022 | 03/11/2022 | Resource Division | 90.44 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 2644/TD | 13/10/2023 | 13/10/2023 | Resource Division | 27.1 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at 2nd TW site for Amarshikasba Zone-I PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000289/2023-2024 | 591/TD | 17/05/2023 | 26/06/2023 | M/S SOURAV MAHAPATRA | 9.2 | 3.76 | 40.9 | 45
5 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 190 Mtrs. Depth) by utilising Departmental Machineries for Amarshi Kasba W/S Scheme (Zone-II,T/W-II) , Patashpur-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000514/2022-2023 | 2117/CDD | 02/03/2023 | 01/04/2023 | MENAKA ENTERPRISE | 15.74 | 14.1 | 89.61 | 100
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE- I Of AMARSHI KASBA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004775131/QUOT/03 DT. 14-06-2024 Application NO- 2004775131 MEMO NO: AMR/PHE/175 DT.14/06/2024 Application type-New connection Consumer Id- 204330575 |  |  | BILL/01335/2024-2025 | BP-2024-25-361 | 01/07/2024 | 01/07/2024 | WBSEDCL | 4.79 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001904/2022-2023 | 805/W/MMD | 24/03/2023 | 20/08/2025 | RITESH AGARWALL | 12.63 | 0 | 0 | 45
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Laying of Left-Out portion HDPE Pipe line of Distribution system by HDPE pipes with allied works of Amarshikasba Zone-I PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000288/2024-2025 | 3053/TD | 19/09/2024 | 18/03/2025 | M/S. NEW DINDA ENTERPRISE | 48.21 | 0 | 0 | 5
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Repair and Renovation of Pump House & Boundary Wall and others allied works for 1st Tube well site at Amarshi Kasba Zone-I Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000359/2024-2025 | 3322/TD | 22/10/2024 | 21/11/2024 | M/S. NEW DINDA ENTERPRISE | 2.76 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Construction of 3rd Pump House & Boundary wall of Amarshi Kasba Zone-I & its adjoining moujas PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000329/2025-2026 | 1716/TD | 30/06/2025 | 09/08/2025 | GOUTAM DEY | 9.9 | 0 | 0 | 0
Total | [13 empty] | 225.02 | 21.57 | 9.59