## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Amarshikashba Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000321/2022-2023 | 591/TD | 17/06/2022 | 07/07/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 3.71 | 87.28 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2022-2023 | 1668/TD | 03/11/2022 | 03/11/2022 | Resource Division | 90.44 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Laying of distribution pipe line to accommodate FHTC (4400 Nos) with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Amarshikasba Zone-I Water Supply Scheme within Patashpur-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 2592/TD | 30/01/2023 | 24/02/2026 | SANKHA ENTERPRISE | 567.28 | 198.8 | 35.04 | 70
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001904/2022-2023 | 805/W/MMD | 24/03/2023 | 20/08/2025 | RITESH AGARWALL | 12.63 | 0 | 0 | 45
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Laying Rising main and other allied works Augmentation of Amarshikasba Zone-I Water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000199/2023-2024 | 400/TD | 27/04/2023 | 07/09/2024 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 12.14 | 4.63 | 38.17 | 75
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at 2nd TW site for Amarshikasba Zone-I PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000289/2023-2024 | 591/TD | 17/05/2023 | 26/06/2023 | M/S SOURAV MAHAPATRA | 9.2 | 3.76 | 40.9 | 45
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 190 Mtrs. Depth) by utilising Departmental Machineries for Amarshi Kasba W/S Scheme (Zone-II,T/W-II) , Patashpur-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000514/2022-2023 | 2117/CDD | 02/03/2023 | 01/04/2023 | MENAKA ENTERPRISE | 15.74 | 14.1 | 89.61 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 2644/TD | 13/10/2023 | 13/10/2023 | Resource Division | 27.1 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Laying of Left-Out portion HDPE Pipe line of Distribution system by HDPE pipes with allied works of Amarshikasba Zone-I PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000288/2024-2025 | 3053/TD | 19/09/2024 | 06/09/2026 | M/S. NEW DINDA ENTERPRISE | 48.21 | 0 | 0 | 5
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Repair and Renovation of Pump House & Boundary Wall and others allied works for 1st Tube well site at Amarshi Kasba Zone-I Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000359/2024-2025 | 3322/TD | 22/10/2024 | 21/11/2024 | M/S. NEW DINDA ENTERPRISE | 2.76 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE- I Of AMARSHI KASBA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004775131/QUOT/03 DT. 14-06-2024 Application NO- 2004775131 MEMO NO: AMR/PHE/175 DT.14/06/2024 Application type-New connection Consumer Id- 204330575 |  |  | BILL/01335/2024-2025 | BP-2024-25-361 | 01/07/2024 | 01/07/2024 | WBSEDCL | 4.79 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | SM/12487 | Augmentation | Construction of 3rd Pump House & Boundary wall of Amarshi Kasba Zone-I & its adjoining moujas PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000329/2025-2026 | 1716/TD | 30/06/2025 | 09/08/2025 | GOUTAM DEY | 9.9 | 0 | 0 | 0
Total | [13 empty] | 804.43 | 225 | 27.97