## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Amarshikashba Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000322/2022-2023 | 617/TD | 21/06/2022 | 11/07/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 3.32 | 78.11 | 100
2 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300 mm X 200mm X 190mm Depth) by utilising Departmental Machineries for Amarshi Kasba W/S Scheme(Z-II,TW-I), Patashpur -I Block under Purba Medinipur District, CDD,P.H.E.Dte. | Driller In Charge | Junior Engineer | ORD/000483/2022-2023 | 2122/CDD | 02/03/2023 | 01/04/2023 | MENAKA ENTERPRISE | 15.74 | 12.47 | 79.24 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000118/2022-2023 | 1669/TD | 03/11/2022 | 03/11/2022 | Resource Division | 57.23 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 2645/TD | 13/10/2023 | 13/10/2023 | Resource Division | 14.4 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Electric Quotation for AMARSIKASBA Water Supply Scheme T/W-I, Zone -II, (Ref. ID-204098661) |  |  | BILL/02897/2023-2024 | BP-2023-24-311 | 01/11/2023 | 01/11/2023 | WBSEDCL | 3.28 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Augmentation of Amarshikasba Zone-II PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-136.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000290/2023-2024 | 592/TD | 17/05/2023 | 01/07/2023 | ANUSKA ENTERPRISE | 21.29 | 7.74 | 36.37 | 40
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site for Augmentation of Amarshikasba Zone-II & its adjoining moujas PWSS in Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer | Junior Engineer | ORD/000291/2023-2024 | 593/TD | 17/05/2023 | 16/07/2023 | M/S SOURAV MAHAPATRA | 7.26 | 5.78 | 79.61 | 100
8 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 190 Mtrs. Depth) by utilising Departmental Machineries for Amarshi Kasba W/S Scheme (Zone-I,T/W-III) , Patashpur-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000515/2022-2023 | 2123/CDD | 02/03/2023 | 27/12/2023 | MENAKA ENTERPRISE | 15.74 | 12.78 | 81.21 | 100
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of AMARSI KASBA W/S Scheme under MMD, PHE, Dte. Block- Potashpur-I, AMARSI C.C.C. Ref. Memo No- 2004607907/QUOT/03 DT. 21-02-2024 Application NO- 2004607907 Application type-New connection Reference Id- 204223198 |  |  | BILL/04384/2023-2024 | BP-2023-24-822 | 13/03/2024 | 13/03/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001971/2022-2023 | 814/W/MMD | 24/03/2023 | 20/09/2023 | S.K.ENTERPRISE | 22.8 | 19.87 | 87.13 | 10
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Laying of distribution pipe line to accommodate FHTC (2238 Nos) with construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Amarshikasba Zone-II water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000750/2022-2023 | 2593/TD | 30/01/2023 | 26/06/2025 | DAS ENTERPRISE | 372.65 | 254.87 | 68.39 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Drum Sheet walling 1.40m. (av.) high on sal-bullah / Eucalyptus bullah pilling with allied works of Amarshi Kasba Zone-II & its adjoining moujas PWSS within Patashpur-I Block under Contai-Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/001257/2024-2025 | 130/CSD | 16/01/2025 | 23/01/2025 | GHOSH CONSTRUCTION (GST : 19AXMPG8403A1ZO) | 0.97 | 0 | 0 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | SM/12488 | Augmentation | Construction of 3.60 mtr x 3.00 mtr. Size Switch Room cum Chlorin Room (as per Departmental Design and Drawing) without sanitary and water supply arrangements including Plinth Protection at 2nd TW site for Augmentation of Amarshikasba Zone-II and its adjoining moujas PWSS in Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (For Low land) | Assistant Engineer | Junior Engineer | ORD/000845/2023-2024 | 18/TD | 03/01/2024 | 30/08/2024 | GOUTAM DEY | 3.75 | 0 | 0 | 100
Total | [13 empty] | 542.54 | 316.83 | 58.4